## sonex776_construction_log
Start Time | End Time | Duration | Total | Description
2009-10-09 14:41 | 2009-10-09 16:59 | 0.095833 | 34.6999 | alodine aft fuse smaller parts
2009-10-09 09:47 | 2009-10-09 13:00 | 0.13403 | 34.6041 | alodine aft fuse smaller parts
2009-10-08 14:00 | 2009-10-08 16:17 | 0.095139 | 34.4701 | alodine aft fuse channel parts
2009-10-04 13:12 | 2009-10-04 14:45 | 0.064583 | 34.3749 | alodine aft fuse longerons
2009-09-13 10:49 | 2009-09-13 11:08 | 0.013194 | 34.3103 | alodine aft fuse longerons
2009-09-13 09:50 | 2009-09-13 10:19 | 0.020139 | 34.2971 | make pvc alodine tube
2009-08-29 18:30 | 2009-08-29 19:09 | 0.027083 | 34.277 | build pvc alodine bath
2009-08-21 19:53 | 2009-08-21 20:21 | 0.019444 | 34.2499 | deburr tailcone parts
2009-08-21 14:24 | 2009-08-21 15:06 | 0.029167 | 34.2305 | deburr tailcone parts
2009-08-21 13:26 | 2009-08-21 14:17 | 0.035417 | 34.2013 | get alodine containers etc.
2009-08-20 19:28 | 2009-08-20 20:09 | 0.028472 | 34.1659 | deburr tailcone parts
2009-08-20 13:54 | 2009-08-20 15:20 | 0.059722 | 34.1374 | deburr tailcone parts
2009-08-20 11:26 | 2009-08-20 13:05 | 0.06875 | 34.0777 | deburr tailcone parts
2009-08-20 09:21 | 2009-08-20 10:39 | 0.054167 | 34.0089 | deburr tailcone parts
2009-08-19 19:05 | 2009-08-19 19:11 | 0.0041667 | 33.9548 | cleanup & deburr tailcone parts (while watching MotoGP)
2009-08-19 17:34 | 2009-08-19 18:52 | 0.054167 | 33.9506 | cleanup & deburr tailcone parts (while watching Isle of Man TT)
2009-08-19 16:06 | 2009-08-19 16:23 | 0.011806 | 33.8964 | cleanup & deburr tailcone parts
2009-08-19 14:08 | 2009-08-19 15:03 | 0.038194 | 33.8846 | cleanup & deburr tailcone parts
2009-08-19 12:53 | 2009-08-19 13:31 | 0.026389 | 33.8464 | cleanup & deburr tailcone parts
2009-08-19 11:25 | 2009-08-19 12:13 | 0.033333 | 33.8201 | cleanup & deburr tailcone parts
2009-08-10 15:23 | 2009-08-10 15:50 | 0.01875 | 33.7867 | F21 disassemble tailcone
2009-08-10 13:16 | 2009-08-10 13:45 | 0.020139 | 33.768 | F21 disassemble tailcone
2009-08-08 14:20 | 2009-08-08 14:48 | 0.019444 | 33.7478 | port timetracker data
2009-08-06 14:14 | 2009-08-06 15:13 | 0.040972 | 33.7284 | F21 disassemble tailcone box
2009-08-06 12:00 | 2009-08-06 12:48 | 0.033333 | 33.6874 | F19 discovered it is too difficult to install the turtledeck without the tailcone box (as well as the turtledeck skins) being rivetted. Decide what to do re corrosion proofing the aft fuse - alodine channels & brackets but leave skins bare. Minimal ZnCr use inside fuse.
2009-08-06 10:38 | 2009-08-06 11:59 | 0.05625 | 33.6541 | F19-02 skin assembly
2009-08-05 21:02 | 2009-08-05 21:40 | 0.026389 | 33.5978 | F19-02 skin assembly
2009-08-03 06:36 | 2009-08-03 07:14 | 0.026389 | 33.5714 | F19-03 splice channel assembly
2009-08-03 06:11 | 2009-08-03 06:36 | 0.017361 | 33.5451 | F20-12 aft clip
2009-08-02 22:36 | 2009-08-02 22:47 | 0.0076389 | 33.5277 | F20-11 fwd clip
2009-08-02 22:14 | 2009-08-02 22:35 | 0.014583 | 33.5201 | F20-10 former clips (6)
2009-07-30 14:33 | 2009-07-30 15:00 | 0.01875 | 33.5055 | F20-10 turtledeck former clips (6)
2009-07-30 14:20 | 2009-07-30 14:33 | 0.0090278 | 33.4867 | F23-08 bend seatbelt attach plates
2009-07-30 13:50 | 2009-07-30 14:20 | 0.020833 | 33.4777 | F20-09RL attach plates (form bends)
2009-07-30 13:30 | 2009-07-30 13:50 | 0.013889 | 33.4569 | F20-07 skin splice channel
2009-07-29 21:00 | 2009-07-29 21:25 | 0.017361 | 33.443 | F20-07 skin splice channel
2009-07-29 20:00 | 2009-07-29 20:30 | 0.020833 | 33.4256 | F21 updrill upper splice plates
2009-07-29 18:00 | 2009-07-29 20:00 | 0.083333 | 33.4048 | F21 install F22-02 aft shear web
2009-07-29 15:23 | 2009-07-29 17:31 | 0.088889 | 33.3214 | F21 install F22-02 aft shear web
2009-07-18 22:41 | 2009-07-19 00:08 | 0.060417 | 33.2326 | F21 updrill x-tie corners to #30 where req.
2009-07-18 22:22 | 2009-07-18 22:41 | 0.013194 | 33.1721 | F21 drill for splice plate bolts
2009-07-16 17:08 | 2009-07-16 17:17 | 0.00625 | 33.1589 | F21 recap, clamp down aft fuse
2009-05-28 17:05 | 2009-05-28 17:12 | 0.0048611 | 33.1527 | F21-01 updrill x-tie/vertical holes
2009-05-28 16:38 | 2009-05-28 16:47 | 0.00625 | 33.1478 | F21-01 updrill x-tie/vertical holes
2009-05-28 16:16 | 2009-05-28 16:37 | 0.014583 | 33.1416 | F21-01 updrill F23-03 fwd tw mount angle
2009-05-28 10:44 | 2009-05-28 11:55 | 0.049306 | 33.127 | F21-01 drill F22-01 lower skin to longerons
2009-05-27 20:55 | 2009-05-27 21:53 | 0.040278 | 33.0777 | F21-01 fit & drill F23-05RL seatbelt mount assemblies
2009-05-27 19:42 | 2009-05-27 20:56 | 0.051389 | 33.0374 | F21-01 updrill side skins to #30
2009-05-27 11:30 | 2009-05-27 12:24 | 0.0375 | 32.986 | F21-01 drill F22-01 lower skin to longerons & x-ties
2009-05-27 10:49 | 2009-05-27 11:30 | 0.028472 | 32.9485 | F21-01 fit F23-03 tailwheel fwd mount angle
2009-05-27 10:16 | 2009-05-27 10:48 | 0.022222 | 32.9201 | F21-01 fit F23-02 tailwheel mount bulkhead
2009-05-26 15:45 | 2009-05-26 17:01 | 0.052778 | 32.8978 | F21-01 fit F23-04 tailwheel mount angle
2009-05-26 13:00 | 2009-05-26 13:50 | 0.034722 | 32.8451 | F21-01 fit F23-04 tailwheel mount angle
2009-05-26 12:20 | 2009-05-26 13:00 | 0.027778 | 32.8103 | F21-01 fit F23-12 x-tie box clips
2009-05-25 19:43 | 2009-05-25 20:39 | 0.038889 | 32.7826 | F21-01 fit x-tie box (trim 1/16 each end)
2009-05-25 15:28 | 2009-05-25 16:09 | 0.028472 | 32.7437 | F21-01 fit x-tie box
2009-05-25 12:45 | 2009-05-25 15:29 | 0.11389 | 32.7152 | F21-01 lower x-ties
2009-05-25 09:38 | 2009-05-25 11:37 | 0.082639 | 32.6013 | F21-01 detail A drill tail wheel mount
2009-05-22 16:08 | 2009-05-22 16:56 | 0.033333 | 32.5187 | F21-01 fit & pilot x-ties
2009-05-21 20:30 | 2009-05-21 21:49 | 0.054861 | 32.4853 | F21-01 fit & drill x-ties
2009-05-21 19:24 | 2009-05-21 20:30 | 0.045833 | 32.4305 | F21-01 drill bottom skin to splice plates
2009-05-20 10:58 | 2009-05-20 12:13 | 0.052083 | 32.3846 | F21-01 square up tail cone box
2009-05-20 10:00 | 2009-05-20 10:47 | 0.032639 | 32.3326 | F21-01 review & layout
2009-05-19 19:58 | 2009-05-19 21:25 | 0.060417 | 32.2999 | F21 review
2009-05-15 17:06 | 2009-05-15 17:29 | 0.015972 | 32.2395 | F22-02 shear web assy
2009-05-15 15:02 | 2009-05-15 15:17 | 0.010417 | 32.2235 | F22-02 shear web assy
2009-05-15 14:55 | 2009-05-15 15:02 | 0.0048611 | 32.2131 | F22 review
2009-05-15 14:13 | 2009-05-15 14:55 | 0.029167 | 32.2083 | F23-12 clips (2)
2009-05-15 14:12 | 2009-05-15 14:14 | 0.0013889 | 32.1791 | reorganise workshop
2009-05-15 12:50 | 2009-05-15 14:12 | 0.056944 | 32.1777 | F23-09/11 pushrod supports
2009-05-14 20:52 | 2009-05-14 21:00 | 0.0055556 | 32.1208 | cleanup
2009-05-14 20:30 | 2009-05-14 20:52 | 0.015278 | 32.1152 | F23-05RL seatbelt mounts
2009-05-14 14:47 | 2009-05-14 15:19 | 0.022222 | 32.0999 | F23-05RL seatbelt mounts
2009-05-14 14:18 | 2009-05-14 14:47 | 0.020139 | 32.0777 | tidyup
2009-05-07 19:47 | 2009-05-07 21:57 | 0.090278 | 32.0576 | F23-05RL seatbelt mounts
2009-05-07 15:57 | 2009-05-07 16:05 | 0.0055556 | 31.9673 | F23-06 seatbelt mount webs (2)
2009-05-07 11:40 | 2009-05-07 13:36 | 0.080556 | 31.9617 | F23-02 bulkhead
2009-05-07 10:44 | 2009-05-07 11:40 | 0.038889 | 31.8812 | F23 gather materials
2009-05-06 21:57 | 2009-05-06 22:14 | 0.011806 | 31.8423 | cleanup
2009-05-06 21:42 | 2009-05-06 21:56 | 0.0097222 | 31.8305 | F24-09 lower x-tie #5
2009-05-06 19:09 | 2009-05-06 19:43 | 0.023611 | 31.8208 | F24-09 lower x-tie #5
2009-05-06 18:07 | 2009-05-06 19:04 | 0.039583 | 31.7971 | F24-06,7,8 lower x-tie channels
2009-05-06 17:29 | 2009-05-06 18:06 | 0.025694 | 31.7576 | F24-05 lower x-tie #1
2009-05-06 17:04 | 2009-05-06 17:29 | 0.017361 | 31.7319 | F24-02,3,4 upper x-tie channels
2009-05-06 14:13 | 2009-05-06 15:50 | 0.067361 | 31.7145 | F24-01 x-tie box assy (#30 clecos)
2009-05-06 13:46 | 2009-05-06 14:13 | 0.01875 | 31.6471 | F24 retrieve channels
2009-05-05 15:42 | 2009-05-05 16:11 | 0.020139 | 31.6284 | F25-01L aft side panel (pilot drill splice plates)
2009-05-05 14:27 | 2009-05-05 15:26 | 0.040972 | 31.6083 | F25-01L aft side panel (pilot drill splice plates)
2009-05-05 11:54 | 2009-05-05 12:40 | 0.031944 | 31.5673 | F25-01L aft side panel (pilot drill vertical channels)
2009-05-05 10:51 | 2009-05-05 11:54 | 0.04375 | 31.5353 | F25-01L aft side panel (pilot drill longerons)
2009-05-04 09:30 | 2009-05-04 11:19 | 0.075694 | 31.4916 | F25-01R fuse aft side panel (splice plates)
2009-05-04 09:00 | 2009-05-04 09:30 | 0.020833 | 31.4159 | F26-012 aft side skin (bend fwd edge @ SERS)
2009-05-01 22:46 | 2009-05-01 23:00 | 0.0097222 | 31.3951 | F26-012 aft side skin (bend fwd edge)
2009-05-01 22:05 | 2009-05-01 22:46 | 0.028472 | 31.3853 | F25-01R aft side panel
2009-05-01 11:52 | 2009-05-01 13:55 | 0.085417 | 31.3569 | F25-01R aft side panel
2009-05-01 11:15 | 2009-05-01 11:52 | 0.025694 | 31.2714 | F26-012 aft side skin (bend fwd edge)
2009-05-01 09:30 | 2009-05-01 11:15 | 0.072917 | 31.2458 | timepanic, stickgrip
2009-04-30 19:43 | 2009-04-30 21:04 | 0.05625 | 31.1728 | F26-02/3R&L longerons
2009-04-30 15:50 | 2009-04-30 16:21 | 0.021528 | 31.1166 | raise lower shelf on workbench
2009-04-30 14:46 | 2009-04-30 15:25 | 0.027083 | 31.0951 | raise lower shelf on workbench
2009-04-26 22:01 | 2009-04-26 22:06 | 0.0034722 | 31.068 | cleanup
2009-04-26 21:48 | 2009-04-26 22:01 | 0.0090278 | 31.0645 | F26-08 rudder stop plate
2009-04-26 21:34 | 2009-04-26 21:48 | 0.0097222 | 31.0555 | F26-07L lower vert. splice plate
2009-04-26 21:15 | 2009-04-26 21:35 | 0.013889 | 31.0458 | F26-06L lower horiz. splice plate
2009-04-26 21:03 | 2009-04-26 21:14 | 0.0076389 | 31.0319 | F26-07R lower vert. splice plate
2009-04-26 20:44 | 2009-04-26 21:03 | 0.013194 | 31.0242 | F26-06R lower horiz. splice plate
2009-04-26 17:41 | 2009-04-26 18:23 | 0.029167 | 31.011 | F26-05R&L upper vert. splice plate
2009-04-26 16:00 | 2009-04-26 16:33 | 0.022917 | 30.9819 | F26-05R&L upper vert. splice plate
2009-04-26 15:19 | 2009-04-26 16:00 | 0.028472 | 30.9589 | F26-04R&L upper horiz splice plate
2009-04-26 15:09 | 2009-04-26 15:18 | 0.00625 | 30.9305 | cleanup
2009-04-26 15:05 | 2009-04-26 15:10 | 0.0034722 | 30.9242 | F27-09 fairlead assy x 4
2009-04-26 14:55 | 2009-04-26 15:05 | 0.0069444 | 30.9208 | F27-10 fairlead mount block x 4
2009-04-26 11:19 | 2009-04-26 12:47 | 0.061111 | 30.9138 | F27-10 fairlead mount block x 4
2009-04-26 09:56 | 2009-04-26 11:20 | 0.058333 | 30.8527 | F27-01L vert. zee
2009-04-25 19:57 | 2009-04-25 21:13 | 0.052778 | 30.7944 | F27-01R vert. zee
2009-04-25 17:57 | 2009-04-25 18:20 | 0.015972 | 30.7416 | F27-02R&L vert. channels
2009-04-25 17:22 | 2009-04-25 17:58 | 0.025 | 30.7256 | F27-03R&L vert. channels
2009-04-25 16:25 | 2009-04-25 17:21 | 0.038889 | 30.7006 | F27-04R&L vert. channels skip trim cable hole
2009-04-25 15:34 | 2009-04-25 16:25 | 0.035417 | 30.6617 | F27-05R&L vert. channels
2009-04-23 12:29 | 2009-04-23 13:05 | 0.025 | 30.6263 | web update
2009-04-23 09:34 | 2009-04-23 10:41 | 0.046528 | 30.6013 | F27 organise channel parts
2009-04-23 07:45 | 2009-04-23 08:11 | 0.018056 | 30.5548 | F27 organise channel parts
2009-04-23 07:00 | 2009-04-23 07:45 | 0.03125 | 30.5367 | W07-01L move left wing to top shed
2009-04-22 21:30 | 2009-04-22 22:23 | 0.036806 | 30.5055 | F27 unpack aft fuse parts
2009-04-22 20:36 | 2009-04-22 21:29 | 0.036806 | 30.4687 | wrap left wing for storage
2009-04-22 17:22 | 2009-04-22 19:10 | 0.075 | 30.4319 | W07-01L fit wingtip
2009-04-22 15:11 | 2009-04-22 15:13 | 0.0013889 | 30.3569 | W07-01L fit wingtip
2009-04-22 13:20 | 2009-04-22 13:39 | 0.013194 | 30.3555 | panel layout design
2009-04-20 14:41 | 2009-04-20 15:30 | 0.034028 | 30.3423 | W07-01L fit wingtip
2009-04-08 18:36 | 2009-04-08 18:50 | 0.0097222 | 30.3083 | W07-01L fit wing tip
2009-04-08 18:23 | 2009-04-08 18:35 | 0.0083333 | 30.2985 | W07-01L check wing twist
2009-04-08 18:06 | 2009-04-08 18:23 | 0.011806 | 30.2902 | W07-01L trim proud rivet stems
2009-04-08 15:59 | 2009-04-08 17:40 | 0.070139 | 30.2784 | W07-01L rivet fwd skin to lower spar cap & ribs
2009-03-28 10:15 | 2009-03-28 11:15 | 0.041667 | 30.2083 | emails
2009-03-26 23:20 | 2009-03-26 23:44 | 0.016667 | 30.1666 | W07-01L rivet fwd skin to bottom spar cap
2009-03-26 22:20 | 2009-03-26 23:19 | 0.040972 | 30.1499 | W07-01L level wing inverted
2009-03-26 22:02 | 2009-03-26 22:20 | 0.0125 | 30.1089 | workshop cleanup
2009-03-21 22:06 | 2009-03-21 22:51 | 0.03125 | 30.0964 | W07-01L rivet fwd skin upper surface to ribs
2009-03-21 13:43 | 2009-03-21 13:51 | 0.0055556 | 30.0652 | W07-01L rivet fwd skin upper surface to ribs
2009-03-21 11:49 | 2009-03-21 12:00 | 0.0076389 | 30.0596 | W07-01L rivet fwd skin upper surface to ribs
2009-03-21 07:45 | 2009-03-21 08:31 | 0.031944 | 30.052 | W07-01L rivet fwd skin upper surface to ribs
2009-03-20 16:45 | 2009-03-20 17:19 | 0.023611 | 30.0201 | W07-01L rivet fwd skin to upper spar cap
2009-03-20 16:15 | 2009-03-20 16:45 | 0.020833 | 29.9964 | W07-01L level wing frame
2009-03-20 14:13 | 2009-03-20 15:25 | 0.05 | 29.9756 | W07-01L square fwd rib flanges
2009-03-20 12:35 | 2009-03-20 13:01 | 0.018056 | 29.9256 | W07-01L ZnCr fwd skin
2009-03-20 11:54 | 2009-03-20 12:35 | 0.028472 | 29.9076 | W07-01L debur fwd skin
2009-03-19 21:45 | 2009-03-19 22:30 | 0.03125 | 29.8791 | W07-01L dimple fwd wing skin
2009-03-19 11:35 | 2009-03-19 12:48 | 0.050694 | 29.8478 | W07-01L dimple fwd wing skin
2009-03-18 20:43 | 2009-03-18 20:57 | 0.0097222 | 29.7971 | W07-01L dimple fwd skin
2009-03-18 19:45 | 2009-03-18 20:43 | 0.040278 | 29.7874 | W18-01L debur fwd skin
2009-03-18 19:08 | 2009-03-18 19:24 | 0.011111 | 29.7471 | W18-01L debur fwd skin
2009-03-18 17:43 | 2009-03-18 18:30 | 0.032639 | 29.736 | collect c-frame
2009-03-18 16:51 | 2009-03-18 17:02 | 0.0076389 | 29.7034 | W07-01L unpack fwd skin
2009-03-18 15:18 | 2009-03-18 16:51 | 0.064583 | 29.6958 | W07-01L install wiring in fwd ribs
2009-03-18 14:57 | 2009-03-18 15:03 | 0.0041667 | 29.6312 | clean up
2009-03-18 13:46 | 2009-03-18 14:57 | 0.049306 | 29.627 | W07-01L aft lower skin rivet to ribs
2009-03-18 12:42 | 2009-03-18 13:47 | 0.045139 | 29.5777 | W07-01L aft lower skin rivet to aft spar
2009-03-18 12:08 | 2009-03-18 12:42 | 0.023611 | 29.5326 | W07-01L level wing frame
2009-03-18 11:42 | 2009-03-18 12:08 | 0.018056 | 29.5089 | W07-01L square up aft rib flanges
2009-03-18 10:57 | 2009-03-18 11:04 | 0.0048611 | 29.4909 | W07-01L square up aft rib flanges
2009-03-18 10:49 | 2009-03-18 10:57 | 0.0055556 | 29.486 | W07-01L level wing frame
2009-03-18 10:19 | 2009-03-18 10:49 | 0.020833 | 29.4805 | W02-F bellcrank rod-end attachment
2009-03-17 17:00 | 2009-03-17 18:06 | 0.045833 | 29.4596 | W19-02L lower aft skin ZnCr
2009-03-17 14:40 | 2009-03-17 15:25 | 0.03125 | 29.4138 | W19-02L lower aft skin debur
2009-03-17 13:57 | 2009-03-17 14:41 | 0.030556 | 29.3826 | W18-02 lhs inspection cover holes
2009-03-17 13:02 | 2009-03-17 13:56 | 0.0375 | 29.352 | unpack left aft lower skin
2009-03-17 11:38 | 2009-03-17 12:40 | 0.043056 | 29.3145 | unpack left aft lower skin
2009-03-13 09:41 | 2009-03-13 10:58 | 0.053472 | 29.2714 | W07-01L rivet aft upper skin to ribs
2009-03-12 16:11 | 2009-03-12 16:55 | 0.030556 | 29.218 | W07-01L rivet aft upper skin to rear spar, avoiding wingwalk area
2009-03-12 15:34 | 2009-03-12 16:10 | 0.025 | 29.1874 | W07-01L ZnCr flap & aileron hinges
2009-03-12 14:59 | 2009-03-12 15:20 | 0.014583 | 29.1624 | W07-01L debur flap & aileron hinges
2009-03-12 14:44 | 2009-03-12 14:59 | 0.010417 | 29.1478 | W07-01L rivet aft upper skin
2009-03-12 14:12 | 2009-03-12 14:34 | 0.015278 | 29.1374 | W07-01L check rib flanges parallel to skin
2009-03-12 12:48 | 2009-03-12 13:46 | 0.040278 | 29.1221 | W07-01L check rib flanges parallel to skin
2009-03-12 12:37 | 2009-03-12 12:49 | 0.0083333 | 29.0819 | W07-01L level left wing frame
2009-03-12 12:09 | 2009-03-12 12:36 | 0.01875 | 29.0735 | workshop cleanup
2009-03-11 11:01 | 2009-03-11 12:22 | 0.05625 | 29.0548 | move excess timber to top shed
2009-03-11 10:10 | 2009-03-11 10:48 | 0.026389 | 28.9985 | move excess timber to top shed
2009-03-10 16:02 | 2009-03-10 16:15 | 0.0090278 | 28.9721 | debur rear spar skin holes
2009-03-10 13:59 | 2009-03-10 16:02 | 0.085417 | 28.9631 | W21-01L complete bellcrank assy & rivet to #9 rib assy
2009-03-08 17:23 | 2009-03-08 17:39 | 0.011111 | 28.8777 | W19-01L ZnCr inside aft upper skin
2009-03-08 15:20 | 2009-03-08 16:20 | 0.041667 | 28.8666 | W19-01L ZnCr inside aft upper skin
2009-03-05 21:50 | 2009-03-05 22:58 | 0.047222 | 28.8249 | W07-01L debur aft upper wing skin
2009-03-04 23:09 | 2009-03-04 23:45 | 0.025 | 28.7777 | W07-01L unpack upper aft skin
2009-03-04 18:13 | 2009-03-04 18:21 | 0.0055556 | 28.7527 | W07-01L unpack upper aft skin
2009-03-04 14:41 | 2009-03-04 17:22 | 0.11181 | 28.7471 | W17-01L rivet root ribs
2009-03-02 17:50 | 2009-03-02 18:42 | 0.036111 | 28.6353 | W14-01L rivet aft spar to ribs
2009-03-02 17:20 | 2009-03-02 17:50 | 0.020833 | 28.5992 | W08-01L rivet outboard vertical stiffener angle
2009-03-01 15:02 | 2009-03-01 17:28 | 0.10139 | 28.5784 | W14-01L rivet left wing ribs gussets difficult due to rivet direction
2009-03-01 14:23 | 2009-03-01 15:03 | 0.027778 | 28.477 | debur & ZnCr left rear spar at rib attach locations
2009-03-01 14:03 | 2009-03-01 14:22 | 0.013194 | 28.4492 | W14-01L rivet left wing ribs
2009-02-26 16:49 | 2009-02-26 17:15 | 0.018056 | 28.436 | attach ribs to left main spar
2009-02-26 15:33 | 2009-02-26 16:38 | 0.045139 | 28.418 | debur left main spar rib & skin holes
2009-02-25 16:36 | 2009-02-25 16:42 | 0.0041667 | 28.3728 | ZnCr rib flanges & spacers
2009-02-25 16:17 | 2009-02-25 16:35 | 0.0125 | 28.3687 | ZnCr rib flanges & spacers
2009-02-14 15:30 | 2009-02-14 16:00 | 0.020833 | 28.3562 | W07-01R move right wing in top shed
2009-02-01 20:07 | 2009-02-01 20:30 | 0.015914 | 28.3353 | W07-01R wrap up right wing for storage
2009-02-01 18:18 | 2009-02-01 18:48 | 0.02059 | 28.3194 | W07-01R wrap up right wing for storage
2009-02-01 12:30 | 2009-02-01 12:49 | 0.013519 | 28.2988 | W07-01R wrap up right wing for storage
2009-01-31 18:52 | 2009-01-31 19:21 | 0.019803 | 28.2853 | W07-01R wrap up right wing for storage
2009-01-31 17:01 | 2009-01-31 17:48 | 0.032963 | 28.2655 | W07-01R rivet wing tip (just a few temp AAP rivets)
2009-01-31 16:13 | 2009-01-31 17:01 | 0.033322 | 28.2325 | W07-01R trim down protruding rivet stems (about 6)
2009-01-31 14:27 | 2009-01-31 16:13 | 0.073495 | 28.1992 | W07-01R fit W20-01R wing root doubler
2009-01-25 14:44 | 2009-01-25 15:36 | 0.03625 | 28.1257 | W07-01R fit wing tip (not finished)
2009-01-25 13:39 | 2009-01-25 13:46 | 0.0046412 | 28.0895 | W07-01R fit wing tip
2009-01-25 12:46 | 2009-01-25 13:39 | 0.037106 | 28.0848 | W07-01R rivet leading edge lower surface (front row)
2009-01-24 21:00 | 2009-01-24 22:02 | 0.042731 | 28.0477 | W07-01R rivet leading edge lower surface
2009-01-24 18:59 | 2009-01-24 19:12 | 0.0088889 | 28.005 | W07-01R rivet leading edge lower surface
2009-01-24 16:25 | 2009-01-24 18:48 | 0.09897 | 27.9961 | W07-01R rivet leading edge upper surface
2009-01-24 14:44 | 2009-01-24 16:25 | 0.069954 | 27.8971 | W07-01R level wing prior to riveting leading edge skin
2009-01-24 13:29 | 2009-01-24 14:44 | 0.051991 | 27.8272 | W07-01R install electrical wiring
2009-01-22 15:33 | 2009-01-22 16:48 | 0.051863 | 27.7752 | W23-08 pitot hose supports (rivet to ribs)
2009-01-19 21:15 | 2009-01-19 21:59 | 0.030556 | 27.7233 | W23-02 alodine pitot assy parts
2009-01-18 17:02 | 2009-01-18 17:18 | 0.011262 | 27.6928 | W23-02 prepare pitot assy parts for alodine
2009-01-18 16:19 | 2009-01-18 17:03 | 0.030243 | 27.6815 | W23 rivet pitot nutplates to skin
2009-01-18 15:26 | 2009-01-18 16:18 | 0.036308 | 27.6513 | W18-01R scotchbrite & ZnCr inside of leading edge skin
2009-01-18 13:51 | 2009-01-18 14:58 | 0.046609 | 27.615 | W23 dimple/csk skin & platenuts for pitot assy
2009-01-18 12:29 | 2009-01-18 13:40 | 0.049444 | 27.5684 | W23 drill leading edge skin for pitot assy
2009-01-17 19:20 | 2009-01-17 20:13 | 0.036505 | 27.5189 | W18-01R fit leading edge and mark holes for pitot assy
2009-01-17 17:21 | 2009-01-17 18:20 | 0.040706 | 27.4824 | W18-01R vacuum reform of leading edge skin
2009-01-17 15:20 | 2009-01-17 16:29 | 0.047813 | 27.4417 | W18-01R vacuum reform of leading edge skin
2009-01-14 22:00 | 2009-01-14 22:52 | 0.035787 | 27.3939 | W23-08 pitot hose supports (drill to ribs)
2009-01-14 10:54 | 2009-01-14 12:57 | 0.085683 | 27.3581 | W23-08 pitot hose supports (fabricate)
2009-01-12 16:00 | 2009-01-12 16:46 | 0.031944 | 27.2724 | W23-08 pitot hose supports
2009-01-11 22:45 | 2009-01-11 23:06 | 0.01441 | 27.2405 | W07-01R unpack leading edge skin
2009-01-11 16:52 | 2009-01-11 17:11 | 0.013275 | 27.2261 | W23-08 pitot hose supports
2009-01-11 14:32 | 2009-01-11 16:52 | 0.097326 | 27.2128 | W07-01R rivet aft lower skin
2009-01-11 13:42 | 2009-01-11 14:09 | 0.018472 | 27.1155 | W07-01R fit aft lower skin & flap hinge
2009-01-11 13:03 | 2009-01-11 13:41 | 0.02669 | 27.097 | W07-01R level wing structure
2009-01-11 12:43 | 2009-01-11 13:03 | 0.013576 | 27.0703 | W07 check tie down bolt can be installed after skin
2009-01-11 12:13 | 2009-01-11 12:44 | 0.021424 | 27.0567 | W07-01R check aft lower rib flanges are 90 degree
2009-01-11 10:40 | 2009-01-11 10:49 | 0.0064699 | 27.0353 | W02 aileron bellcrank control rod end attachments
2009-01-10 17:01 | 2009-01-10 17:39 | 0.026435 | 27.0288 | W02 aileron bellcrank control rod end attachments
2009-01-10 16:25 | 2009-01-10 16:35 | 0.0072801 | 27.0024 | W02 aileron bellcrank control rod end attachments
2009-01-03 15:00 | 2009-01-03 15:28 | 0.019479 | 26.9951 | W19 rhs lower skin ZnCr
2009-01-03 12:34 | 2009-01-03 13:13 | 0.02706 | 26.9756 | W19 rhs lower skin debur
2009-01-03 12:01 | 2009-01-03 12:21 | 0.013681 | 26.9486 | W19 rhs lower skin debur
2009-01-03 08:35 | 2009-01-03 09:15 | 0.02765 | 26.9349 | W19 rhs lower skin access hole
2009-01-03 08:03 | 2009-01-03 08:36 | 0.022593 | 26.9072 | W19 retrieve rhs lower skin from storage
2009-01-02 22:47 | 2009-01-02 23:11 | 0.016632 | 26.8847 | clean up workshop
2009-01-02 15:40 | 2009-01-02 16:46 | 0.046007 | 26.868 | W07-01R rivet aft upper skin
2009-01-02 13:56 | 2009-01-02 15:18 | 0.056771 | 26.822 | W07-01R rivet aft upper skin
2009-01-02 12:18 | 2009-01-02 13:56 | 0.067998 | 26.7652 | W07-01R check aft upper rib flanges are 90 degree
2009-01-02 11:35 | 2009-01-02 11:43 | 0.0058565 | 26.6972 | W07-01R rivet aft upper skin
2009-01-02 11:16 | 2009-01-02 11:34 | 0.012616 | 26.6914 | W07-01R level wing structure
2009-01-01 19:08 | 2009-01-01 20:13 | 0.045012 | 26.6788 | W21 aileron bellcrank final assembly
2009-01-01 18:23 | 2009-01-01 19:08 | 0.03147 | 26.6338 | wing wiring grommets
2009-01-01 16:11 | 2009-01-01 17:02 | 0.03515 | 26.6023 | clear shelf under bench to make space for skin
2009-01-01 15:07 | 2009-01-01 16:11 | 0.044144 | 26.5671 | W19 ZnCr rhs aft upper wing skin
2009-01-01 12:59 | 2009-01-01 13:54 | 0.038449 | 26.523 | W19 debur rhs aft upper wing skin
2009-01-01 12:44 | 2009-01-01 12:52 | 0.0058565 | 26.4845 | W19 debur rhs aft upper wing skin
2008-12-29 21:20 | 2008-12-29 21:48 | 0.019213 | 26.4787 | W17 bolt RHS root ribs to spars
2008-12-29 17:10 | 2008-12-29 18:00 | 0.034468 | 26.4595 | W17 bolt RHS root ribs to spars
2008-12-29 13:26 | 2008-12-29 14:59 | 0.064491 | 26.425 | W17 rivet RHS root ribs to attach brackets
2008-11-30 15:24 | 2008-11-30 16:28 | 0.044433 | 26.3605 | W23-01 pitot/static/aoa assembly (bend tubes)
2008-11-30 12:00 | 2008-11-30 13:17 | 0.053171 | 26.3161 | W23-05 pitot/static/aoa assembly (mount plate)
2008-11-29 20:42 | 2008-11-30 01:43 | 0.20932 | 26.2629 | W23-02 pitot/static/aoa assembly (phenolic triple clamp)
2008-11-29 14:16 | 2008-11-29 16:40 | 0.099803 | 26.0536 | W23-02 pitot/static/aoa assembly (phenolic triple clamp)
2008-11-29 13:00 | 2008-11-29 14:16 | 0.053056 | 25.9538 | W02 un-wrap right wing structure again!
2008-11-28 16:07 | 2008-11-28 17:03 | 0.038588 | 25.9007 | W02 wrap up right wing structure for storage
2008-11-28 13:21 | 2008-11-28 16:07 | 0.1151 | 25.8622 | W02 aileron pushrod installation
2008-11-06 10:13 | 2008-11-06 11:00 | 0.032824 | 25.747 | W17 remove root rib attach brackets & debur
2008-11-06 09:16 | 2008-11-06 10:11 | 0.038044 | 25.7142 | W14-01R rivet aft spar to ribs (rib #1 aft bracket)
2008-11-05 21:01 | 2008-11-05 21:31 | 0.020787 | 25.6762 | W14-01R rivet aft spar to ribs
2008-11-05 12:14 | 2008-11-05 16:39 | 0.18417 | 25.6554 | W14-01R rivet ribs to main spar
2008-11-05 09:11 | 2008-11-05 09:59 | 0.033634 | 25.4712 | W14-01R ZnCr mating surfaces of ribs/spacers etc.
2008-11-04 20:00 | 2008-11-04 20:53 | 0.036609 | 25.4376 | W14-01R prepare to rivet ribs to main spar
2008-11-02 18:30 | 2008-11-02 19:34 | 0.044225 | 25.401 | W21-01L/R rivet #9 rib assembies
2008-11-01 22:31 | 2008-11-02 00:22 | 0.076782 | 25.3568 | W21-02R bellcrank pivot assemby (press/ream bushings etc.)
2008-11-01 16:51 | 2008-11-01 17:11 | 0.013623 | 25.28 | W21-02L bellcrank pivot assembly (press/ream bushings etc.)
2008-11-01 13:44 | 2008-11-01 16:24 | 0.11093 | 25.2664 | W21-02L bellcrank pivot assembly (press/ream bushings etc.)
2008-10-29 17:00 | 2008-10-29 17:58 | 0.040347 | 25.1554 | W15 rivet gussets to aft left wing ribs
2008-10-26 22:12 | 2008-10-26 22:46 | 0.023773 | 25.1151 | W15 rivet gussets to front left wing ribs
2008-10-25 08:22 | 2008-10-25 09:13 | 0.035602 | 25.0913 | W15 rivet gussets to aft right wing ribs
2008-10-24 22:37 | 2008-10-24 23:43 | 0.046053 | 25.0557 | W15 rivet gussets to front right wing ribs
2008-10-24 12:41 | 2008-10-24 12:55 | 0.010012 | 25.0097 | ZnCr wing rib gussets
2008-10-23 22:00 | 2008-10-23 22:29 | 0.020301 | 24.9996 | study plans, prepare to rivet gussets to wing ribs
2008-10-21 16:05 | 2008-10-21 17:35 | 0.062766 | 24.9793 | wash / etch / alodine right gussets / spacers / bellcrank parts
2008-10-21 14:36 | 2008-10-21 15:30 | 0.037581 | 24.9166 | wash / etch / alodine left gussets / spacers / bellcrank parts
2008-10-20 14:46 | 2008-10-20 21:29 | 0.28006 | 24.879 | wash / etch / alodine all wing ribs
2008-10-18 08:00 | 2008-10-18 09:33 | 0.064606 | 24.5989 | acetone fwd ribs & gussets etc.
2008-10-17 12:00 | 2008-10-17 14:55 | 0.12137 | 24.5343 | debur & smooth rhs fwd ribs
2008-10-10 20:00 | 2008-10-10 21:17 | 0.053264 | 24.413 | clean wing ribs (acetone)
2008-10-10 14:32 | 2008-10-10 15:21 | 0.033866 | 24.3597 | misc deburring of internal wing parts
2008-10-10 14:07 | 2008-10-10 14:32 | 0.017176 | 24.3258 | W21 aileron bellcrank assemblies (fit bushings)
2008-09-08 16:41 | 2008-09-08 17:33 | 0.036111 | 24.3087 | debur edges right aft ribs
2008-09-07 17:46 | 2008-09-07 18:25 | 0.027083 | 24.2725 | debur edges right aft ribs
2008-09-07 15:38 | 2008-09-07 17:25 | 0.074306 | 24.2455 | debur edges left aft ribs
2008-09-06 21:00 | 2008-09-06 22:00 | 0.041667 | 24.1712 | debur holes left aft ribs
2008-09-04 20:30 | 2008-09-04 21:30 | 0.041667 | 24.1295 | debur holes right aft ribs
2008-09-01 22:04 | 2008-09-01 23:00 | 0.038889 | 24.0878 | debur left leading edge ribs
2008-09-01 16:53 | 2008-09-01 17:28 | 0.024306 | 24.0489 | debur left leading edge ribs
2008-08-01 11:10 | 2008-08-01 13:16 | 0.0875 | 24.0246 | drill attach holes to 1/4'
2008-07-31 14:05 | 2008-07-31 15:10 | 0.045139 | 23.9371 | W08 mate main spars and drill alignment holes to 1/4'
2008-07-30 14:58 | 2008-07-30 15:20 | 0.015278 | 23.892 | rivet right spar -10 csk tight
2008-07-30 14:51 | 2008-07-30 14:58 | 0.0048611 | 23.8767 | rivet right spar -12 csk
2008-07-30 14:33 | 2008-07-30 14:51 | 0.0125 | 23.8719 | rivet right spar -10 csk
2008-07-30 13:50 | 2008-07-30 14:33 | 0.029861 | 23.8594 | rivet right spar -8 csk
2008-07-29 22:35 | 2008-07-29 22:50 | 0.010417 | 23.8295 | rivet right spar -8 csk
2008-07-29 22:13 | 2008-07-29 22:35 | 0.015278 | 23.8191 | rivet right spar -12 csk
2008-07-29 20:57 | 2008-07-29 22:13 | 0.052778 | 23.8038 | rivet right spar -8,10,12
2008-07-29 11:50 | 2008-07-29 12:15 | 0.017361 | 23.751 | rivet right spar -7
2008-07-29 10:26 | 2008-07-29 11:50 | 0.058333 | 23.7337 | rivet right spar -6
2008-07-28 20:30 | 2008-07-28 22:05 | 0.065972 | 23.6753 | rivet right spar -6
2008-07-28 14:30 | 2008-07-28 15:50 | 0.055556 | 23.6094 | rivet right spar -6
2008-07-09 16:39 | 2008-07-09 17:25 | 0.031944 | 23.5538 | rivet upper stiffener, check all rivets in left spar (16 bad)
2008-07-09 13:29 | 2008-07-09 14:34 | 0.045139 | 23.5219 | make thin riveting bolt
2008-06-05 15:46 | 2008-06-05 16:10 | 0.016667 | 23.4767 | redrill aft root rib to attach angle #30
2008-06-05 14:30 | 2008-06-05 15:46 | 0.052778 | 23.46 | W07-01L remove skins
2008-06-04 20:45 | 2008-06-04 22:24 | 0.06875 | 23.4073 | W07-01L drill leading edge lower side to ribs, front row, final drill to spar #30 and ribs #31
2008-05-22 21:13 | 2008-05-22 22:38 | 0.058935 | 23.3385 | W18-01L re-form leading edge radius (vacuum method attempt #4, with 34mm galv pipe)
2008-05-15 21:26 | 2008-05-15 22:36 | 0.048414 | 23.2796 | W07-01L drill fwd skin to ribs #40 (lower surface)
2008-05-09 16:06 | 2008-05-09 16:39 | 0.022812 | 23.2312 | W07-01L fit W20-01L root doubler
2008-05-09 15:38 | 2008-05-09 16:06 | 0.019306 | 23.2084 | W07-01L drill fwd skin to upper spar cap #30
2008-05-08 22:33 | 2008-05-08 23:12 | 0.027025 | 23.1891 | W07-01L drill fwd skin to ribs #31 (upper surface)
2008-05-07 08:58 | 2008-05-07 10:17 | 0.054896 | 23.162 | W07-01L drill fwd skin to ribs (upper surface)
2008-05-06 21:13 | 2008-05-06 22:07 | 0.037222 | 23.1071 | W07-01L cleco aft skins & fit fwd skin
2008-05-02 14:35 | 2008-05-02 15:29 | 0.037477 | 23.0699 | W07-01L fit fwd root rib
2008-05-01 13:27 | 2008-05-01 15:06 | 0.069074 | 23.0324 | W07-01L remove aft skins, install fwd ribs
2008-05-01 13:01 | 2008-05-01 13:16 | 0.010752 | 22.9634 | W07-01L remove aft skins, install fwd ribs
2008-04-30 11:38 | 2008-04-30 13:16 | 0.068299 | 22.9526 | W18-01L re-form leading edge radius (vacuum method attempt #3 - success!)
2008-04-27 14:00 | 2008-04-27 15:30 | 0.0625 | 22.8843 | W18-01L re-form leading edge radius (vacuum method attempt #2)
2008-04-26 20:00 | 2008-04-26 23:00 | 0.125 | 22.8218 | W18-01L re-form leading edge radius (vacuum method attempt #1)
2008-04-24 18:03 | 2008-04-24 18:24 | 0.014514 | 22.6968 | W07-01L final drill upper aft skin to #30 (except main spar & root doubler area)
2008-04-24 17:14 | 2008-04-24 17:48 | 0.023449 | 22.6823 | W07-01L final drill upper aft skin to #30 (except main spar & root doubler area)
2008-04-24 16:51 | 2008-04-24 17:14 | 0.016238 | 22.6588 | W07-01L re-level wing (top side up)
2008-04-24 15:38 | 2008-04-24 16:51 | 0.050718 | 22.6426 | W07-01L final drill lower aft skin to #30 (except main spar & root doubler area)
2008-04-24 15:09 | 2008-04-24 15:38 | 0.019931 | 22.5919 | W07-01L re-level wing (upside down)
2008-04-10 22:45 | 2008-04-11 00:06 | 0.056435 | 22.572 | W07-01L drill aileron & flap hinges to aft spar
2008-04-09 22:23 | 2008-04-09 22:49 | 0.018229 | 22.5155 | W07-01L reattach aft upper skin
2008-04-09 20:57 | 2008-04-09 22:23 | 0.059734 | 22.4973 | W21-01L drill bellcrank support to lower skin
2008-04-09 13:31 | 2008-04-09 15:49 | 0.095579 | 22.4376 | W07-01L fit aft lower skin (drill #40 to ribs & main spar)
2008-04-09 12:11 | 2008-04-09 12:58 | 0.032778 | 22.342 | W07-01L fit aft lower skin (drill #40 to aft spar)
2008-04-09 10:47 | 2008-04-09 11:45 | 0.040243 | 22.3092 | W07-01L fit aft lower skin
2008-04-09 10:09 | 2008-04-09 10:14 | 0.003287 | 22.269 | W07-01L fit aft lower skin
2008-04-09 09:56 | 2008-04-09 10:09 | 0.0091551 | 22.2657 | W07-01L re-level wing upside-down
2008-03-30 00:10 | 2008-03-30 00:58 | 0.033681 | 22.2565 | W07-01L re-level wing upside-down
2008-03-29 22:50 | 2008-03-30 00:10 | 0.055359 | 22.2228 | W21-01L drill bellcrank support to upper skin
2008-03-29 15:55 | 2008-03-29 17:14 | 0.05515 | 22.1675 | W07-01L fit aft upper skin (drill to ribs & main spar)
2008-03-27 20:37 | 2008-03-27 22:23 | 0.073866 | 22.1123 | W07-01L fit aft upper skin (drill to aft spar)
2008-03-26 21:44 | 2008-03-26 22:08 | 0.016447 | 22.0385 | W07-01L fit aft upper skin
2008-03-26 20:50 | 2008-03-26 21:45 | 0.03794 | 22.022 | W17-01L aft root rib fit & drill
2008-03-26 14:54 | 2008-03-26 15:00 | 0.0039468 | 21.9841 | W17-01L aft root rib fit & drill
2008-03-25 09:20 | 2008-03-25 10:02 | 0.029225 | 21.9801 | W14-01L attach aft ribs to spar
2008-03-25 08:54 | 2008-03-25 09:20 | 0.018113 | 21.9509 | W07-01L engrave ribs & gussets
2008-03-24 14:26 | 2008-03-24 14:59 | 0.023171 | 21.9328 | W07-01R engrave aft ribs & gussets
2008-03-24 11:36 | 2008-03-24 14:26 | 0.11837 | 21.9096 | work out where I was up to!
2008-03-22 14:19 | 2008-03-22 15:12 | 0.037153 | 21.7912 | unpack spars after move from KII to Burnie
2007-12-15 16:16 | 2007-12-15 18:00 | 0.072257 | 21.7541 | packing for move from King Island to Burnie (flaps)
2007-11-19 15:41 | 2007-11-19 17:59 | 0.095694 | 21.6818 | W07-01R dimple fwd skin
2007-11-19 14:13 | 2007-11-19 15:40 | 0.060451 | 21.5861 | W07-01R debur fwd skin
2007-11-19 14:04 | 2007-11-19 14:13 | 0.0062384 | 21.5257 | W07-01R engrave fwd ribs & gussets
2007-11-18 20:30 | 2007-11-18 22:30 | 0.083333 | 21.5195 | W07-01R debur & dimple fwd ribs (at home on couch)
2007-11-18 17:12 | 2007-11-18 17:49 | 0.025845 | 21.4361 | W07-01R debur fwd skin (outer surface)
2007-11-15 13:44 | 2007-11-15 14:23 | 0.027257 | 21.4103 | W21-01R wing rib #9 assembly (drill to upper skin)
2007-11-15 13:05 | 2007-11-15 13:36 | 0.021227 | 21.383 | W07-01R remove lower skin to access rib #9 assy
2007-11-15 11:59 | 2007-11-15 12:59 | 0.041898 | 21.3618 | W07-01R final drill lower aft skin to #30
2007-11-15 11:28 | 2007-11-15 11:59 | 0.021262 | 21.3199 | W07-01R reinstall upper skin
2007-11-15 11:20 | 2007-11-15 11:28 | 0.005625 | 21.2986 | W07-01R drill skin for tie down bolt
2007-11-15 09:57 | 2007-11-15 11:20 | 0.057546 | 21.293 | W21-01R wing rib #9 assembly (drill to lower skin)
2007-11-14 13:34 | 2007-11-14 14:44 | 0.048322 | 21.2355 | W21-01L wing rib #9 assembly
2007-11-14 11:35 | 2007-11-14 13:16 | 0.070266 | 21.1871 | W21-01R wing rib #9 assembly
2007-11-14 09:54 | 2007-11-14 11:34 | 0.069421 | 21.1169 | WT wing tank planning (filler location, drawn on W23)
2007-11-10 16:56 | 2007-11-10 17:56 | 0.041632 | 21.0475 | W21-01R wing rib #9 assembly
2007-11-10 16:14 | 2007-11-10 16:56 | 0.029178 | 21.0058 | W07-01R remove upper aft skin
2007-11-10 13:51 | 2007-11-10 16:14 | 0.098958 | 20.9766 | W07-01R final drill (#30) upper aft skin to aft spar
2007-11-10 12:37 | 2007-11-10 13:45 | 0.047477 | 20.8777 | W07-01R final drill (#30) upper aft skin to ribs
2007-11-10 12:16 | 2007-11-10 12:38 | 0.014988 | 20.8302 | W07-01R remove fwd skin & ribs
2007-11-10 10:18 | 2007-11-10 12:15 | 0.081331 | 20.8152 | W07-01R final drill (1/8') fwd skin to ribs (upper surface)
2007-10-24 16:10 | 2007-10-24 16:48 | 0.026632 | 20.7339 | W07-01R redrill upper spar cap holes to #30
2007-10-24 15:00 | 2007-10-24 16:11 | 0.049178 | 20.7073 | W07-01R final drill (1/8') fwd skin to ribs (lower surface)
2007-10-24 13:06 | 2007-10-24 13:31 | 0.017523 | 20.6581 | W07-01R final drill (1/8') fwd skin to ribs (lower surface)
2007-10-24 12:39 | 2007-10-24 13:06 | 0.018426 | 20.6406 | W07-01R redrill lower spar cap holes to #30
2007-10-24 11:32 | 2007-10-24 12:40 | 0.047002 | 20.6221 | W07 countersunk rivet dimple test
2007-10-24 10:21 | 2007-10-24 11:32 | 0.049144 | 20.5751 | W17-01R fit right fwd root rib
2007-10-24 09:38 | 2007-10-24 10:20 | 0.029491 | 20.526 | W07-01R fit fwd skin (drill lower surface to ribs - fwd row)
2007-10-17 14:00 | 2007-10-17 16:07 | 0.08853 | 20.4965 | W07-01R fit fwd skin (drill lower surface to ribs)
2007-10-17 11:21 | 2007-10-17 13:20 | 0.082558 | 20.408 | W07-01R fit fwd skin (cleco to lower spar cap)
2007-10-17 09:31 | 2007-10-17 11:22 | 0.076852 | 20.3254 | W07-01R fit fwd skin (drill upper surface to ribs)
2007-10-15 16:09 | 2007-10-15 16:24 | 0.010313 | 20.2486 | W07-01R fit fwd skin (cleco to upper spar cap)
2007-10-15 15:15 | 2007-10-15 16:02 | 0.032662 | 20.2382 | W07-01R fit fwd skin (refit leading edge ribs)
2007-10-15 11:17 | 2007-10-15 13:26 | 0.089907 | 20.2056 | W07-01R fit flap hinge (drill to wing)
2007-10-15 09:20 | 2007-10-15 11:17 | 0.081435 | 20.1157 | W07-01R fit flap hinge (trim edge with router)
2007-10-14 16:57 | 2007-10-14 17:50 | 0.036528 | 20.0342 | W07-01R fit aileron & hinge
2007-10-14 14:56 | 2007-10-14 15:41 | 0.031238 | 19.9977 | W07-01R fit aileron & hinge
2007-10-09 14:00 | 2007-10-09 16:00 | 0.083333 | 19.9665 | W07-01R fit aft lower skin (drill to main spar)
2007-10-09 12:03 | 2007-10-09 13:34 | 0.063032 | 19.8831 | W07-01R fit aft lower skin (drill to ribs)
2007-10-09 11:11 | 2007-10-09 12:03 | 0.036377 | 19.8201 | W07-01R fit aft lower skin (drill to aft spar)
2007-10-09 09:48 | 2007-10-09 11:11 | 0.057523 | 19.7837 | W07-01R fit aft lower skin (level, check alignments)
2007-10-08 18:25 | 2007-10-08 19:06 | 0.028206 | 19.7262 | W07-01R fit aft upper skin (drill to main spar)
2007-10-08 16:31 | 2007-10-08 18:25 | 0.078889 | 19.698 | W07-01R fit aft upper skin (drill to ribs)
2007-10-08 13:15 | 2007-10-08 13:29 | 0.0098264 | 19.6191 | W07-01R fit aft upper skin (drill to aft spar)
2007-10-08 10:23 | 2007-10-08 13:16 | 0.11997 | 19.6093 | W07-01R fit aft upper skin (check alignments)
2007-10-07 13:00 | 2007-10-07 13:37 | 0.025498 | 19.4893 | W07-01R fit aft upper skin
2007-10-05 15:39 | 2007-10-05 17:28 | 0.075775 | 19.4638 | W17-01R aft root rib fit & drill
2007-10-05 14:02 | 2007-10-05 15:39 | 0.067396 | 19.388 | W14-01R level wing structure
2007-10-05 12:17 | 2007-10-05 12:34 | 0.01147 | 19.3206 | W14-01R prepare for skinning (cleco aft ribs)
2007-10-05 11:00 | 2007-10-05 12:17 | 0.053414 | 19.3092 | W14-01L ribs/gussets redrill #30
2007-10-05 10:48 | 2007-10-05 10:59 | 0.0078472 | 19.2558 | W14-01L debur rear spar/rib holes
2007-10-05 08:50 | 2007-10-05 10:48 | 0.082106 | 19.2479 | W14-01L ribs/spar redrill to #30
2007-09-30 11:02 | 2007-09-30 12:26 | 0.058519 | 19.1658 | W14-01R ribs/spar redrill to #30
2007-09-30 09:28 | 2007-09-30 11:02 | 0.065278 | 19.1073 | W08 root rib attach angles (bolt to spar)
2007-09-30 08:02 | 2007-09-30 09:27 | 0.059039 | 19.042 | W17 root ribs (notch, fit gussets)
2007-09-25 15:00 | 2007-09-25 15:47 | 0.03265 | 18.983 | W17 root ribs (notch, fit gussets)
2007-09-25 14:05 | 2007-09-25 15:00 | 0.038102 | 18.9503 | W14-01RL drill aft spars to #30
2007-09-25 12:41 | 2007-09-25 12:48 | 0.0048032 | 18.9122 | W17 root ribs (+search for 3 missing nose ribs??)
2007-09-25 10:11 | 2007-09-25 12:41 | 0.10387 | 18.9074 | W15-01L fit fwd ribs
2007-09-24 13:46 | 2007-09-24 16:29 | 0.11328 | 18.8036 | W15-01R fit fwd ribs
2007-09-24 10:17 | 2007-09-24 12:26 | 0.089803 | 18.6903 | W15 fwd ribs (gussets/notches)
2007-09-24 09:44 | 2007-09-24 10:18 | 0.023264 | 18.6005 | W15 fwd ribs (get organised)
2007-09-01 09:12 | 2007-09-01 11:58 | 0.11547 | 18.5772 | W14-01RL fit aft ribs
2007-09-01 08:25 | 2007-09-01 09:11 | 0.032106 | 18.4617 | W16 aft ribs (fwd notches)
2007-08-31 14:05 | 2007-08-31 15:39 | 0.06522 | 18.4296 | W16 aft ribs (fwd notches)
2007-08-31 13:36 | 2007-08-31 14:05 | 0.020266 | 18.3644 | W16 aft ribs (drill gussets)
2007-08-31 12:56 | 2007-08-31 13:18 | 0.015069 | 18.3441 | W16 aft ribs (drill gussets)
2007-08-31 12:36 | 2007-08-31 12:56 | 0.013669 | 18.3291 | W16 aft ribs (get organised)
2007-08-31 11:03 | 2007-08-31 12:36 | 0.064722 | 18.3154 | W17-02 thru -09 root rib gussets
2007-08-30 15:34 | 2007-08-30 16:46 | 0.049676 | 18.2507 | W17-02 thru -09 root rib gussets
2007-08-30 14:01 | 2007-08-30 15:34 | 0.064803 | 18.201 | W16-08 aft lower gussets (x8)
2007-08-30 13:44 | 2007-08-30 14:00 | 0.011447 | 18.1362 | W16-07 aft upper gussets (x8)
2007-08-30 13:12 | 2007-08-30 13:20 | 0.0054514 | 18.1248 | W16-07 aft upper gussets (x8)
2007-08-29 13:24 | 2007-08-29 14:40 | 0.052442 | 18.1193 | W16-07 aft upper gussets (x8)
2007-08-29 11:00 | 2007-08-29 12:24 | 0.058275 | 18.0669 | W15-07 fwd lower gussets (x8)
2007-08-29 09:31 | 2007-08-29 11:00 | 0.061875 | 18.0086 | W15-06 fwd upper gussets (x8)
2007-08-27 15:43 | 2007-08-27 16:27 | 0.030451 | 17.9467 | W15-06 fwd upper gussets (x8)
2007-08-27 13:49 | 2007-08-27 15:43 | 0.079132 | 17.9163 | W15-08/-09 rib gusset blanks (x32)
2007-08-27 09:28 | 2007-08-27 12:20 | 0.11941 | 17.8371 | W15-08/-09 rib gusset blanks (x32)
2007-08-26 09:55 | 2007-08-26 15:45 | 0.24334 | 17.7177 | Build wooden frame to hold Al. sheet stock parts vertically
2007-08-26 09:43 | 2007-08-26 09:55 | 0.0080671 | 17.4744 | W15-08/-09 rib gusset blanks (find .025 sheet)
2007-08-26 09:27 | 2007-08-26 09:43 | 0.011354 | 17.4663 | W17-02 thru -09 root rib gussets
2007-08-21 16:06 | 2007-08-21 16:20 | 0.0098958 | 17.455 | W17-02 thru -09 root rib gussets (find channel)
2007-08-21 15:13 | 2007-08-21 16:05 | 0.036181 | 17.4451 | W21-09 aileron bellcrank mount clips (x8)
2007-08-21 13:49 | 2007-08-21 15:12 | 0.057928 | 17.4089 | F10-16 elevator idler assembly (mistake in pivot hole position)
2007-08-21 12:15 | 2007-08-21 12:54 | 0.026979 | 17.3509 | F10-16 elevator idler assembly
2007-08-21 12:00 | 2007-08-21 12:15 | 0.010509 | 17.324 | F10-21 elevator idler plate
2007-08-21 09:06 | 2007-08-21 11:59 | 0.12031 | 17.3135 | W21-02RL bellcrank pivot assemblies
2007-08-20 13:48 | 2007-08-20 14:45 | 0.039502 | 17.1931 | W21-08 bellcrank spacer (make from 2 x 1/8' Al instead of 1/4 phenolic)
2007-08-20 13:31 | 2007-08-20 13:48 | 0.011817 | 17.1536 | W21-05 bellcrank spacer (make from 2 x 1/8' Al instead of 1/4 phenolic)
2007-08-20 11:41 | 2007-08-20 12:46 | 0.044803 | 17.1418 | W21-05 bellcrank spacer (make from 2 x 1/8' Al instead of 1/4 phenolic)
2007-08-18 15:11 | 2007-08-18 16:32 | 0.056273 | 17.097 | W21-02RL aileron bellcrank assemblies (find parts)
2007-08-18 13:52 | 2007-08-18 15:12 | 0.055255 | 17.0408 | W14-03 web spacers (x16)
2007-08-18 11:57 | 2007-08-18 13:52 | 0.079931 | 16.9855 | W14-02 centre spacers (x20)
2007-08-16 14:49 | 2007-08-16 16:11 | 0.057118 | 16.9056 | W08-01L main spar (bolts)
2007-08-16 14:29 | 2007-08-16 14:49 | 0.014132 | 16.8484 | cleanup
2007-08-16 14:15 | 2007-08-16 14:28 | 0.0093403 | 16.8343 | W12-01 rear spars (bolts)
2007-08-16 13:22 | 2007-08-16 14:15 | 0.036748 | 16.825 | W12-01L rear spar (rivet)
2007-08-16 12:05 | 2007-08-16 12:48 | 0.029769 | 16.7882 | W12-01R rear spar (rivet)
2007-08-16 11:38 | 2007-08-16 12:06 | 0.019132 | 16.7585 | W12-01 rear spar parts (ZnCr)
2007-08-15 14:30 | 2007-08-15 16:54 | 0.10001 | 16.7393 | W12-01 rear spar parts (alodine)
2007-08-15 10:55 | 2007-08-15 12:40 | 0.072986 | 16.6393 | W12-01 rear spar parts (debur)
2007-07-14 10:57 | 2007-07-14 12:10 | 0.050729 | 16.5663 | W12-01 rear spar parts (debur)
2007-07-09 15:40 | 2007-07-09 16:08 | 0.019201 | 16.5156 | W12-01 rear spar parts (debur)
2007-07-09 15:22 | 2007-07-09 15:39 | 0.012141 | 16.4964 | cleanup
2007-07-09 13:36 | 2007-07-09 15:22 | 0.073669 | 16.4843 | W12-01L rear spar assembly (layout, drill, cleco)
2007-07-09 11:31 | 2007-07-09 12:52 | 0.056296 | 16.4106 | W12-01L rear spar assembly (layout, drill, cleco)
2007-07-07 14:15 | 2007-07-07 14:26 | 0.0079398 | 16.3543 | cleanup
2007-07-07 09:58 | 2007-07-07 14:14 | 0.17771 | 16.3464 | W12-01R rear spar assembly (layout, drill, cleco)
2007-07-06 13:14 | 2007-07-06 15:54 | 0.11111 | 16.1686 | W12-02RL rear spar channels (layout/drill holes)
2007-07-05 16:00 | 2007-07-05 16:57 | 0.039583 | 16.0575 | W12-02R rear spar channel (layout rib holes)
2007-07-05 14:51 | 2007-07-05 15:59 | 0.047303 | 16.018 | W13-01 attach plates (pilot drill, debur)
2007-07-05 13:39 | 2007-07-05 14:51 | 0.050127 | 15.9706 | rear spar parts collection
2007-07-04 13:23 | 2007-07-04 15:26 | 0.08515 | 15.9205 | W08-01R main spar (set up for riveting)
2007-07-04 13:15 | 2007-07-04 13:23 | 0.0053935 | 15.8354 | W08-01R main spar (fuel tank ideas)
2007-07-03 15:23 | 2007-07-03 15:56 | 0.023171 | 15.83 | W08-01R main spar (fuel tank ideas)
2007-07-03 13:07 | 2007-07-03 15:23 | 0.094757 | 15.8068 | W08-01R main spar (install bolts)
2007-07-03 11:24 | 2007-07-03 13:07 | 0.071215 | 15.712 | W08-01 main spars (tidy up and cleco)
2007-07-01 16:35 | 2007-07-01 17:03 | 0.019167 | 15.6408 | W11-10 tie down fittings (3/8 hole)
2007-07-01 15:52 | 2007-07-01 16:35 | 0.030035 | 15.6217 | W11-02/06 wing attach assemblies (bolt, stepdrill)
2007-07-01 12:23 | 2007-07-01 15:52 | 0.14527 | 15.5916 | W08-01 main spars (tidy up and cleco)
2007-06-30 08:58 | 2007-06-30 13:03 | 0.16998 | 15.4464 | W08-01 main spar (alodine short webs)
2007-06-29 12:51 | 2007-06-29 16:55 | 0.16972 | 15.2764 | W08-01 main spar (alodine main webs)
2007-06-26 11:22 | 2007-06-26 16:59 | 0.23412 | 15.1067 | W08-01 main spar (alodine main webs)
2007-06-25 13:02 | 2007-06-25 16:55 | 0.16155 | 14.8725 | W08-01 main spar (alodine parts)
2007-06-25 08:59 | 2007-06-25 10:31 | 0.063681 | 14.711 | W08-01 main spar (alodine parts)
2007-06-22 16:53 | 2007-06-22 16:57 | 0.0027546 | 14.6473 | clean up
2007-06-22 14:24 | 2007-06-22 16:54 | 0.10403 | 14.6446 | W20-02&03 root rib attach angles (drill to spars)
2007-06-22 12:00 | 2007-06-22 13:04 | 0.044201 | 14.5405 | W20-02&03 root rib attach angles (drill to spars)
2007-06-22 08:54 | 2007-06-22 11:56 | 0.12647 | 14.4963 | W20-02&03 root rib attach angles (cut, drill, debur)
2007-06-19 14:43 | 2007-06-19 16:46 | 0.085498 | 14.3699 | W20-02&03 root rib attach angles (cut & drill)
2007-06-19 14:40 | 2007-06-19 14:42 | 0.0015394 | 14.2844 | W20-03 (1/2) root rib attach angle (close to 86 degrees)
2007-06-19 14:30 | 2007-06-19 14:40 | 0.006875 | 14.2828 | W20-03 (1/2) root rib attach angle (close to 86 degrees)
2007-06-19 14:24 | 2007-06-19 14:29 | 0.00375 | 14.2759 | W20-02 (2/2) root rib attach angle (open to 94 degrees)
2007-06-19 13:21 | 2007-06-19 14:25 | 0.044282 | 14.2722 | W20-02 (1/2) root rib attach angle (open to 94 degrees)
2007-06-19 12:00 | 2007-06-19 13:20 | 0.055556 | 14.2279 | store flaps & ailerons, review main wing spars
2007-05-22 21:28 | 2007-05-22 21:51 | 0.015706 | 14.1724 | tidy up work area
2007-05-22 21:16 | 2007-05-22 21:28 | 0.0082755 | 14.1567 | W03-01RL install counterweights
2007-05-22 20:11 | 2007-05-22 21:14 | 0.043715 | 14.1484 | W03-01L aileron assembly (rivet)
2007-05-22 18:49 | 2007-05-22 20:11 | 0.056944 | 14.1047 | W03-01R aileron assembly (rivet)
2007-05-22 18:22 | 2007-05-22 18:49 | 0.018646 | 14.0477 | W03-03 rivet counterbalances
2007-05-22 16:34 | 2007-05-22 17:43 | 0.047882 | 14.0291 | W03-03 rivet counterbalances, drive plates etc.
2007-05-22 15:51 | 2007-05-22 15:55 | 0.0029861 | 13.9812 | W03-01RL aileron skins ZnCr
2007-05-22 15:09 | 2007-05-22 15:50 | 0.028588 | 13.9782 | W03-01RL aileron skins ZnCr
2007-05-22 13:00 | 2007-05-22 13:27 | 0.018785 | 13.9496 | W03-01RL aileron parts ZnCr
2007-05-22 11:12 | 2007-05-22 12:12 | 0.041343 | 13.9308 | ZnCr + pie oven incident (oops)
2007-05-22 10:49 | 2007-05-22 11:11 | 0.01559 | 13.8895 | W03-01L aileron skin debur
2007-05-22 09:26 | 2007-05-22 10:32 | 0.045671 | 13.8739 | W03-01L aileron skin debur
2007-05-20 15:50 | 2007-05-20 16:04 | 0.0093866 | 13.8282 | tidy up work area
2007-05-20 14:44 | 2007-05-20 15:46 | 0.043229 | 13.8188 | W03-01R aileron skin debur
2007-05-20 12:28 | 2007-05-20 14:44 | 0.094583 | 13.7756 | W03-01RL alodine parts & cleanup
2007-05-20 11:41 | 2007-05-20 12:06 | 0.017465 | 13.681 | W03-01RL alodine setup
2007-05-20 11:29 | 2007-05-20 11:41 | 0.0081597 | 13.6636 | W03-01RL ailerons (acetone parts)
2007-05-20 10:59 | 2007-05-20 11:29 | 0.020833 | 13.6554 | W03-01RL ailerons (debur parts)
2007-05-20 09:00 | 2007-05-20 10:43 | 0.071782 | 13.6346 | W03-01RL ailerons (debur parts)
2007-05-17 15:55 | 2007-05-17 16:29 | 0.02353 | 13.5628 | W03-01RL ailerons (debur parts)
2007-05-17 14:43 | 2007-05-17 15:54 | 0.049248 | 13.5393 | W03-01RL ailerons (disassemble, redrill #30)
2007-05-17 13:55 | 2007-05-17 14:26 | 0.021748 | 13.49 | W04-09 gap to skin email query
2007-05-17 13:34 | 2007-05-17 13:55 | 0.014259 | 13.4683 | W03-01RL ailerons (disassemble, redrill #30)
2007-05-17 12:37 | 2007-05-17 13:03 | 0.017789 | 13.454 | W03-01L aileron (de-swarth, redrill to #30)
2007-05-16 15:01 | 2007-05-16 15:41 | 0.027581 | 13.4362 | W03-01L aileron (de-swarth, redrill to #30)
2007-05-16 13:39 | 2007-05-16 15:01 | 0.057153 | 13.4086 | W03-01R aileron (de-swarth, redrill to #30)
2007-05-16 13:06 | 2007-05-16 13:38 | 0.022153 | 13.3515 | W03-01R aileron (drill & cleco ribs #40)
2007-05-16 11:51 | 2007-05-16 13:02 | 0.049444 | 13.3293 | W03-01R aileron (drill & cleco ribs #40)
2007-05-16 11:07 | 2007-05-16 11:40 | 0.023241 | 13.2799 | W03-01L aileron (drill & cleco ribs #40)
2007-05-16 08:25 | 2007-05-16 11:07 | 0.11219 | 13.2566 | W03-01RL ailerons (layout & drill skin #40)
2007-05-14 15:18 | 2007-05-14 17:08 | 0.076123 | 13.1445 | W03-01RL ailerons (layout & drill skin #40)
2007-05-14 11:09 | 2007-05-14 12:53 | 0.072095 | 13.0683 | W03-01RL ailerons (layout & drill skin #40)
2007-05-14 10:48 | 2007-05-14 11:00 | 0.008044 | 12.9962 | W03-01RL ailerons (layout & drill skin #40)
2007-05-14 10:33 | 2007-05-14 10:48 | 0.010521 | 12.9882 | workshop cleanup
2007-05-12 21:42 | 2007-05-12 23:16 | 0.065197 | 12.9777 | W03-03 aileron counterbalance assemblies
2007-05-12 20:36 | 2007-05-12 21:42 | 0.045961 | 12.9125 | W03-03 counterbalance (drill lead 3/16)
2007-05-12 13:17 | 2007-05-12 15:09 | 0.077998 | 12.8665 | W03-03 counterbalance (drill lead #40)
2007-05-12 11:47 | 2007-05-12 12:54 | 0.04669 | 12.7885 | W04-08 aileron counterbalance lead weights (2)
2007-05-12 11:41 | 2007-05-12 11:47 | 0.0040394 | 12.7418 | W03-03 aileron counterbalance assemblies (2)
2007-05-12 09:53 | 2007-05-12 11:40 | 0.074387 | 12.7378 | W04-01RL aileron skins (notches)
2007-05-12 07:59 | 2007-05-12 09:54 | 0.079537 | 12.6634 | W04-01L aileron skin (end angle)
2007-05-10 14:42 | 2007-05-10 16:09 | 0.060139 | 12.5839 | W04-01R aileron skin (end angle)
2007-05-10 14:00 | 2007-05-10 14:42 | 0.029213 | 12.5237 | W04-09 aileron counterbalance mount channels
2007-05-09 13:00 | 2007-05-09 13:29 | 0.02044 | 12.4945 | W04-09 aileron counterbalance mount channels
2007-05-09 12:16 | 2007-05-09 12:57 | 0.028148 | 12.4741 | W04-09 search for channel parts
2007-05-09 11:37 | 2007-05-09 12:16 | 0.026956 | 12.4459 | W04-05 aileron root ribs assemblies
2007-05-09 11:17 | 2007-05-09 11:37 | 0.014155 | 12.419 | W04-04 aileron drive plates
2007-05-09 09:29 | 2007-05-09 11:17 | 0.074676 | 12.4048 | W04-06 aileron hinges
2007-05-04 12:07 | 2007-05-04 15:51 | 0.15587 | 12.3301 | W05-01L flap assembly (debur, chromate, rivet)
2007-05-03 11:08 | 2007-05-03 12:08 | 0.041667 | 12.1743 | W05-01L flap assembly (debur skin)
2007-04-30 17:27 | 2007-04-30 18:24 | 0.039468 | 12.1326 | W05-01R flap assembly (rivet)
2007-04-30 17:09 | 2007-04-30 17:26 | 0.011933 | 12.0931 | W05-01R flap assembly (cleco)
2007-04-30 15:49 | 2007-04-30 17:09 | 0.055741 | 12.0812 | W05-01R flap assembly (zinc-chromate skin interior)
2007-04-14 07:34 | 2007-04-14 09:32 | 0.082037 | 12.0255 | W05-01R flap assembly (debur skin)
2007-04-13 13:52 | 2007-04-13 14:33 | 0.028183 | 11.9434 | W05-01R flap assembly (debur skin)
2007-04-12 14:53 | 2007-04-12 17:27 | 0.10716 | 11.9152 | clean up work area, review plans
2007-03-14 07:21 | 2007-03-14 08:06 | 0.031539 | 11.8081 | T02-01 rivet elevator root assembly in place
2007-03-13 16:10 | 2007-03-13 16:43 | 0.02309 | 11.7765 | T06-02 rivet elevator root assembly
2007-03-13 15:48 | 2007-03-13 16:10 | 0.015255 | 11.7534 | T02-01 trial fit elevators to HS
2007-03-13 15:21 | 2007-03-13 15:48 | 0.018646 | 11.7382 | T02-03 rivet elevator (right)
2007-03-13 14:39 | 2007-03-13 15:21 | 0.02912 | 11.7195 | T02-03 rivet elevator (left)
2007-03-13 14:21 | 2007-03-13 14:23 | 0.0014699 | 11.6904 | T02-03 rivet elevator (left)
2007-03-13 11:05 | 2007-03-13 12:23 | 0.053831 | 11.689 | T02-03 elevator skins interior zinc chromate
2007-03-11 16:49 | 2007-03-11 17:12 | 0.015694 | 11.6351 | T02-03 elevator assembly preparation
2007-03-11 16:39 | 2007-03-11 16:49 | 0.0067014 | 11.6194 | clean up
2007-03-11 15:50 | 2007-03-11 16:39 | 0.034109 | 11.6127 | T02-03 elevator skin debur (right)
2007-03-11 15:31 | 2007-03-11 15:42 | 0.007338 | 11.5786 | T02-03 elevator skin debur (right)
2007-03-11 14:57 | 2007-03-11 15:22 | 0.017477 | 11.5713 | T02-03 elevator skin debur (right)
2007-03-05 17:03 | 2007-03-05 17:13 | 0.0066088 | 11.5538 | tidy up work area
2007-03-05 15:52 | 2007-03-05 17:02 | 0.048715 | 11.5472 | T02-03 elevator skin debur (left)
2007-03-05 14:30 | 2007-03-05 15:27 | 0.039317 | 11.4985 | T02-02 HS assembly (rivet lower surface)
2007-03-05 12:14 | 2007-03-05 12:35 | 0.014444 | 11.4592 | T02-02 HS assembly (rivet lower surface)
2007-03-04 15:20 | 2007-03-04 16:36 | 0.052477 | 11.4447 | T02-02 HS assembly (rivet upper surface)
2007-03-02 14:27 | 2007-03-02 15:47 | 0.055613 | 11.3922 | T02-02 HS assembly
2007-03-02 13:57 | 2007-03-02 14:27 | 0.02066 | 11.3366 | T02-02 HS skin chromate inside surface
2007-03-02 12:48 | 2007-03-02 13:57 | 0.047616 | 11.316 | T02-02 HS skin debur (visitors; ed, andrew)
2007-03-02 10:57 | 2007-03-02 12:35 | 0.068299 | 11.2684 | T02-02 HS skin debur (visitors; ed, andrew)
2007-02-27 14:16 | 2007-02-27 14:36 | 0.013924 | 11.2001 | T02-02 HS skin debur
2007-02-27 13:50 | 2007-02-27 14:15 | 0.017581 | 11.1861 | T14-03 VS tip trial fit
2007-02-24 10:55 | 2007-02-24 11:50 | 0.038056 | 11.1686 | T08-02 rivet rudder assembly
2007-02-24 09:13 | 2007-02-24 10:55 | 0.070903 | 11.1305 | T08-02 rudder skin debur & zinc chromate
2007-02-23 15:17 | 2007-02-23 15:47 | 0.020637 | 11.0596 | T08-02 rudder parts collection
2007-02-23 13:49 | 2007-02-23 14:36 | 0.032396 | 11.039 | T08-01 VS rivet skin (left side)
2007-02-22 15:18 | 2007-02-22 15:54 | 0.024896 | 11.0066 | T08-01 VS rivet skin (right side)
2007-02-22 13:53 | 2007-02-22 15:18 | 0.059039 | 10.9817 | T08-01 VS sub-structure (drill out and re-rivet T10-01)
2007-02-21 16:42 | 2007-02-21 16:47 | 0.0037963 | 10.9226 | cleanup
2007-02-21 16:29 | 2007-02-21 16:42 | 0.0087963 | 10.9188 | rivet VS skin (aborted - found mistake in sub-structure)
2007-02-21 15:51 | 2007-02-21 16:29 | 0.026366 | 10.91 | zinc chromate inside of VS skin
2007-02-21 14:35 | 2007-02-21 15:51 | 0.052905 | 10.8837 | alodine VS skin (dubious results)
2007-02-21 10:42 | 2007-02-21 10:50 | 0.0057176 | 10.8308 | prepare for alodining VS skin
2007-02-13 15:30 | 2007-02-13 16:10 | 0.027998 | 10.825 | T11-01 VS skin prep
2007-02-13 14:48 | 2007-02-13 15:21 | 0.022708 | 10.797 | W06-05L/R rivet flap drive assemblies
2007-02-13 13:49 | 2007-02-13 14:47 | 0.040532 | 10.7743 | T02-02 rivet HS sub-structure
2007-02-10 17:20 | 2007-02-10 17:43 | 0.016134 | 10.7338 | T02-02 rivet HS sub-structure
2007-02-10 14:19 | 2007-02-10 16:33 | 0.093322 | 10.7177 | T02-02 rivet HS sub-structure
2007-02-10 09:10 | 2007-02-10 10:05 | 0.038391 | 10.6244 | T13-02 rudder drive horn assy (rivet)
2007-02-07 13:41 | 2007-02-07 14:39 | 0.040185 | 10.586 | T08-01 VS sub-structure (rivet)
2007-02-07 12:09 | 2007-02-07 12:36 | 0.0186 | 10.5458 | T09-02 VS fwd spar assy (rivet)
2007-02-06 13:43 | 2007-02-06 15:33 | 0.07647 | 10.5272 | T09-01 VS main spar assy (bolt & rivet) (first ever rivets!!)
2007-02-06 11:46 | 2007-02-06 12:21 | 0.024039 | 10.4507 | T09-01 VS main spar assy
2007-02-06 11:20 | 2007-02-06 11:46 | 0.017928 | 10.4267 | prepare to alodine VS skin
2007-02-06 10:39 | 2007-02-06 11:02 | 0.015741 | 10.4087 | prepare to alodine VS skin
2007-02-05 14:54 | 2007-02-05 17:48 | 0.12117 | 10.393 | alodine HS, elevator & flap parts
2007-02-05 14:26 | 2007-02-05 14:54 | 0.01919 | 10.2718 | setup alodine line
2007-02-05 11:05 | 2007-02-05 12:14 | 0.047639 | 10.2526 | deburr HS parts
2007-02-05 10:09 | 2007-02-05 11:05 | 0.038889 | 10.205 | construct PVC alodine tube
2007-02-03 09:48 | 2007-02-03 14:31 | 0.19671 | 10.1661 | engrave & deburr HS, elevator & flap parts
2007-01-13 13:33 | 2007-01-13 16:46 | 0.13405 | 9.9694 | alodine VS and rudder parts
2007-01-13 11:13 | 2007-01-13 12:22 | 0.047604 | 9.8353 | deburr VS and rudder parts
2007-01-13 10:17 | 2007-01-13 11:13 | 0.038854 | 9.7877 | find rudder parts
2007-01-13 09:14 | 2007-01-13 09:56 | 0.029502 | 9.7489 | alodine setup
2007-01-06 14:07 | 2007-01-06 14:48 | 0.028623 | 9.7194 | continue deburring & smoothing tail parts pre alodine
2007-01-06 12:24 | 2007-01-06 14:06 | 0.071134 | 9.6908 | T06-06 clip remake (lost original)
2006-11-19 16:54 | 2006-11-19 17:26 | 0.022269 | 9.6196 | T028-02 HS substructure cleco (to find parts)
2006-11-13 12:12 | 2006-11-13 12:32 | 0.013681 | 9.5974 | T028-02 HS substructure cleco (to find parts)
2006-11-13 11:19 | 2006-11-13 12:12 | 0.036956 | 9.5837 | T08-01 VS substructure cleco (to find parts)
2006-11-13 10:31 | 2006-11-13 11:18 | 0.032488 | 9.5467 | T11-01 deburr VS skin
2006-11-10 16:24 | 2006-11-10 17:10 | 0.032245 | 9.5142 | unpack & sort tail parts (after KI move)
2006-11-10 14:51 | 2006-11-10 16:15 | 0.058519 | 9.482 | W11-xxL parts debur
2006-11-10 14:31 | 2006-11-10 14:51 | 0.013831 | 9.4235 | W11-xxR parts debur
2006-11-10 12:03 | 2006-11-10 12:42 | 0.026875 | 9.4096 | W11-xxR parts debur
2006-11-07 13:42 | 2006-11-07 14:30 | 0.033634 | 9.3828 | W11-xxR parts debur
2006-11-07 12:19 | 2006-11-07 12:59 | 0.027512 | 9.3491 | W11-01R lower angle deburr
2006-11-07 11:11 | 2006-11-07 12:19 | 0.047234 | 9.3216 | workshop setup (mount vice, sander etc)
2006-11-07 10:57 | 2006-11-07 11:11 | 0.009456 | 9.2744 | W11-01R lower angle deburr
2006-11-06 14:37 | 2006-11-06 15:38 | 0.042211 | 9.2649 | W08-01R main spar assy (cleco)
2006-11-06 12:37 | 2006-11-06 13:13 | 0.024977 | 9.2227 | W08-01R main spar assy (deburr webs + doublers)
2006-11-06 12:05 | 2006-11-06 12:37 | 0.022141 | 9.1977 | W08-01R main spar assy (deburr spar cap holes)
2006-11-06 11:54 | 2006-11-06 12:05 | 0.0073843 | 9.1756 | find old pics
2006-11-06 11:26 | 2006-11-06 11:54 | 0.019688 | 9.1682 | work area clean up
2006-11-04 13:30 | 2006-11-04 14:04 | 0.023576 | 9.1485 | W08-01R main spar assy (csk 3/16 holes)
2006-11-04 12:51 | 2006-11-04 13:30 | 0.02691 | 9.125 | W08-01R main spar assy (csk spar cap 5/32 holes)
2006-11-04 11:16 | 2006-11-04 12:51 | 0.066169 | 9.098 | W08-01R main spar assy (csk centre web 5/32 holes)
2006-10-13 17:42 | 2006-10-13 17:48 | 0.0043519 | 9.0319 | W08-01R main spar assy (csk centre web 5/32 holes)
2006-10-13 14:56 | 2006-10-13 17:41 | 0.11455 | 9.0275 | W08-01R main spar assy (dimple main web)
2006-10-13 10:15 | 2006-10-13 11:09 | 0.037627 | 8.913 | W08-01R main spar assy (dimple main web)
2006-10-13 09:38 | 2006-10-13 10:15 | 0.025822 | 8.8753 | W08-01L/R reassemble after move to King Island
2006-10-12 15:32 | 2006-10-12 16:27 | 0.038009 | 8.8495 | W08-01L/R reassemble after move to King Island
2006-04-24 22:13 | 2006-04-24 23:11 | 0.040347 | 8.8115 | W08-01L main spar assy (deburr spar cap holes)
2006-04-21 23:03 | 2006-04-22 00:32 | 0.061528 | 8.7712 | W08-01L main spar assy (csk spar cap extrusion)
2006-04-21 21:23 | 2006-04-21 22:43 | 0.055752 | 8.7096 | W08-01L main spar assy (csk centre web 3/16 holes)
2006-04-21 19:08 | 2006-04-21 20:00 | 0.035984 | 8.6539 | W08-01L main spar assy (csk centre web 5/32 holes)
2006-04-21 17:56 | 2006-04-21 18:53 | 0.039248 | 8.6179 | W08-01L main spar assy (dimple aft web)
2006-04-21 17:43 | 2006-04-21 17:46 | 0.0019097 | 8.5787 | W08-01L main spar assy (dimple aft web)
2006-04-20 21:06 | 2006-04-20 23:15 | 0.089792 | 8.5767 | W05-01L flap assembly (ribs, redrill #30)
2006-04-20 18:03 | 2006-04-20 19:16 | 0.051042 | 8.487 | W05-01L flap (drill pilot holes in skin)
2006-04-19 19:35 | 2006-04-19 20:53 | 0.053831 | 8.4359 | W05-01R flap assembly (redrill to #30)
2006-04-14 15:31 | 2006-04-14 16:34 | 0.0436 | 8.3821 | W05-01R flap assembly (drill rib holes)
2006-04-14 10:50 | 2006-04-14 12:22 | 0.064167 | 8.3385 | W05-01R flap assembly (drill rib holes)
2006-04-14 00:20 | 2006-04-14 02:19 | 0.082454 | 8.2743 | W05-01R flap assembly (drill hinge into place)
2006-04-10 22:44 | 2006-04-10 23:19 | 0.024375 | 8.1919 | W06-05R&L flap drive assemblies
2006-04-10 22:07 | 2006-04-10 22:44 | 0.025382 | 8.1675 | W06-01L flap skin
2006-04-09 21:14 | 2006-04-09 22:27 | 0.05103 | 8.1421 | W04-01R aileron skin (confusing!)
2006-04-09 20:41 | 2006-04-09 21:14 | 0.022674 | 8.0911 | W06-01L flap skin
2006-04-09 17:04 | 2006-04-09 18:16 | 0.049687 | 8.0684 | W06-06R&L flap hinges
2006-04-08 15:37 | 2006-04-08 16:24 | 0.032662 | 8.0187 | W06-01R flap skin
2006-04-08 14:32 | 2006-04-08 15:04 | 0.022326 | 7.9861 | W06-01R flap skin
2006-04-01 23:58 | 2006-04-02 01:44 | 0.073438 | 7.9637 | W10-04R&L tip webs
2006-04-01 18:54 | 2006-04-01 19:14 | 0.014097 | 7.8903 | clean up work area
2006-04-01 18:20 | 2006-04-01 18:54 | 0.023438 | 7.8762 | W08-01R main spar assembly (drill 3/16 holes x 18)
2006-04-01 17:35 | 2006-04-01 18:20 | 0.030995 | 7.8528 | W08-01R main spar assembly (final drill to #21)
2006-04-01 15:52 | 2006-04-01 17:30 | 0.067743 | 7.8218 | W08-01R main spar assembly (final drill to #21)
2006-04-01 | 2006-04-01 01:57 | 0.0814 | 7.754 | W08-01R main spar assembly (final drill to #21)
2006-03-30 23:06 | 2006-03-31 00:10 | 0.044676 | 7.6726 | W08-01L main spar assembly (drill 3/16 holes x 18)
2006-03-30 20:01 | 2006-03-30 23:06 | 0.12853 | 7.6279 | W08-01L main spar assembly (final drill to #21)
2006-03-30 17:23 | 2006-03-30 18:31 | 0.047072 | 7.4994 | W08-01L main spar assembly (final drill to #21)
2006-03-30 15:18 | 2006-03-30 16:44 | 0.059907 | 7.4523 | W08-01L main spar assembly (final drill to #21)
2006-03-29 23:03 | 2006-03-29 23:54 | 0.035613 | 7.3924 | W08-01L main spar assembly (prepare for final drilling)
2006-03-29 20:00 | 2006-03-29 20:30 | 0.021065 | 7.3568 | W08-01L main spar assembly (prepare for final drilling)
2006-03-28 22:22 | 2006-03-28 23:58 | 0.066748 | 7.3358 | W08-01R main spar assembly (prepare for final drilling)
2006-03-28 00:42 | 2006-03-28 01:58 | 0.052766 | 7.269 | root angle layout / pilot drill (left spar)
2006-03-27 20:48 | 2006-03-27 22:15 | 0.060324 | 7.2162 | root angle layout / pilot drill (right spar)
2006-03-27 19:46 | 2006-03-27 19:54 | 0.0058102 | 7.1559 | root angle layout / pilot drill (right spar)
2006-03-27 19:31 | 2006-03-27 19:46 | 0.010613 | 7.1501 | clean up work area
2006-03-27 18:51 | 2006-03-27 19:31 | 0.027488 | 7.1395 | W11-06 root wing attach assembly (2/2)
2006-03-26 23:09 | 2006-03-26 23:43 | 0.023299 | 7.112 | W11-06 root wing attach assembly (1/2)
2006-03-26 22:19 | 2006-03-26 23:08 | 0.03397 | 7.0887 | W11-02 end wing attach assembly (2/2)
2006-03-26 19:42 | 2006-03-26 21:10 | 0.061123 | 7.0547 | W11-02 end wing attach assembly (1/2)
2006-03-26 18:41 | 2006-03-26 19:42 | 0.042141 | 6.9936 | W11-03 wing attach blocks (2,3,4/4)
2006-03-26 15:23 | 2006-03-26 16:53 | 0.062269 | 6.9515 | W11-03 wing attach blocks (1/4)
2006-03-26 12:46 | 2006-03-26 14:48 | 0.084861 | 6.8892 | W11-01 lower spar angles (2)
2006-03-26 11:50 | 2006-03-26 12:45 | 0.038519 | 6.8043 | organise wing spar angle parts
2006-03-25 22:30 | 2006-03-26 | 0.062153 | 6.7658 | W08-01L main wing spar (redrill to #30)
2006-03-25 20:26 | 2006-03-25 20:46 | 0.013935 | 6.7037 | W08-01L main wing spar (redrill to #30)
2006-03-25 16:56 | 2006-03-25 18:32 | 0.066933 | 6.6897 | W08-01R main wing spar (redrill to #30)
2006-03-25 15:02 | 2006-03-25 16:12 | 0.048623 | 6.6228 | W08-01R main wing spar (drill holes #40)
2006-03-25 12:20 | 2006-03-25 14:07 | 0.07419 | 6.5742 | W08-01R main wing spar (drill holes #40)
2006-03-25 10:26 | 2006-03-25 11:59 | 0.064699 | 6.5 | W08-01L main wing spar (drill holes #40)
2006-03-24 23:44 | 2006-03-25 01:21 | 0.067685 | 6.4353 | W08-01L main wing spar (drill holes #40)
2006-03-24 20:52 | 2006-03-24 22:53 | 0.084051 | 6.3676 | W08-01L main wing spar (fit main web)
2006-03-23 23:10 | 2006-03-23 23:34 | 0.016481 | 6.2836 | W08-01L main wing spar (fit main web)
2006-03-23 22:08 | 2006-03-23 23:11 | 0.043414 | 6.2671 | wooden spar support blocks
2006-03-22 21:59 | 2006-03-22 22:24 | 0.017604 | 6.2237 | wooden spar support blocks
2006-03-22 18:40 | 2006-03-22 19:52 | 0.049919 | 6.2061 | W08-01R&L main wing spar assemblies
2006-03-22 18:26 | 2006-03-22 18:40 | 0.0095949 | 6.1561 | organise wing spar parts
2006-03-21 22:19 | 2006-03-21 23:03 | 0.030602 | 6.1465 | W10-07 x 2
2006-03-21 21:48 | 2006-03-21 22:19 | 0.021586 | 6.1159 | 0.032 sheet parts layout
2006-03-21 20:29 | 2006-03-21 21:01 | 0.022546 | 6.0944 | organise wing spar parts
2006-03-21 20:03 | 2006-03-21 20:23 | 0.013819 | 6.0718 | debur tail parts
2006-03-20 20:20 | 2006-03-20 21:53 | 0.064294 | 6.058 | debur tail parts
2006-03-20 19:23 | 2006-03-20 19:28 | 0.0036227 | 5.9937 | debur tail parts
2006-03-19 13:36 | 2006-03-19 15:59 | 0.099468 | 5.9901 | debur tail parts
2006-03-18 16:10 | 2006-03-18 18:54 | 0.11418 | 5.8906 | debur tail parts
2006-01-18 22:37 | 2006-01-18 22:38 | 0.00053241 | 5.7764 | AN3 (3/16) bolt hole problem (holes are too tight?)
2006-01-18 22:03 | 2006-01-18 22:37 | 0.023692 | 5.7759 | T12-04 (drill 1' hole)
2006-01-18 21:04 | 2006-01-18 21:16 | 0.008125 | 5.7522 | T12-04 (drill 1' hole)
2006-01-18 20:24 | 2006-01-18 21:04 | 0.027928 | 5.7441 | disassemble VS & rudder
2006-01-14 14:37 | 2006-01-14 15:17 | 0.027616 | 5.7161 | T14-03 vertical tail tip
2006-01-13 21:56 | 2006-01-13 22:17 | 0.01463 | 5.6885 | T14-03 vertical tail tip (need dremel cut-off wheel)
2006-01-12 21:50 | 2006-01-13 00:10 | 0.097361 | 5.6739 | T08-02 rudder assy
2006-01-12 19:15 | 2006-01-12 20:54 | 0.06897 | 5.5765 | T08-02 rudder assy
2006-01-11 21:42 | 2006-01-11 22:02 | 0.013727 | 5.5076 | T08-02 rudder assembly (cleco hinge)
2006-01-11 21:08 | 2006-01-11 21:42 | 0.023576 | 5.4938 | T13-07 rudder hinge
2006-01-11 19:48 | 2006-01-11 20:30 | 0.029398 | 5.4703 | T13-02 rudder drive horn assy (+ T13-06 clip)
2006-01-11 19:10 | 2006-01-11 19:47 | 0.025949 | 5.4409 | T13-03 rudder drive horn (bend + chamfer)
2006-01-10 21:48 | 2006-01-10 22:25 | 0.025706 | 5.4149 | T13-03 rudder drive horn (drill holes)
2006-01-10 20:35 | 2006-01-10 21:47 | 0.050255 | 5.3892 | T13-01 rudder skin
2006-01-07 00:30 | 2006-01-07 00:53 | 0.01625 | 5.339 | clean up and rudder assembly review
2006-01-07 | 2006-01-07 00:30 | 0.020752 | 5.3227 | T08-01 redrill skin to #30
2006-01-06 23:34 | 2006-01-06 23:59 | 0.01765 | 5.302 | T10-06 upper hinge (drill into place)
2006-01-06 22:57 | 2006-01-06 23:34 | 0.02559 | 5.2843 | T08-01 redrill skin to #30
2006-01-05 22:54 | 2006-01-05 22:58 | 0.0027315 | 5.2587 | pondering mistake in T10-05 LE rib position (forgot to install T12-07 before drilling rib)
2006-01-05 22:24 | 2006-01-05 22:54 | 0.020891 | 5.256 | T08-01 skin attach
2006-01-05 21:52 | 2006-01-05 22:02 | 0.0066782 | 5.2351 | T08-01 skin attach
2006-01-05 20:08 | 2006-01-05 21:27 | 0.054815 | 5.2284 | T08-01 skin attach
2006-01-04 23:16 | 2006-01-05 00:02 | 0.032199 | 5.1736 | T08-01 VS frame (redrill to #30)
2006-01-04 23:10 | 2006-01-04 23:15 | 0.0035069 | 5.1414 | T08-01 VS frame (T10-05 LE rib)
2006-01-04 22:34 | 2006-01-04 23:10 | 0.025266 | 5.1379 | T08-01 VS frame (pilot drill ribs etc)
2006-01-04 21:33 | 2006-01-04 22:04 | 0.021539 | 5.1126 | T08-01 VS frame (pilot drill ribs etc)
2006-01-04 20:35 | 2006-01-04 21:06 | 0.021273 | 5.0911 | T10-04 VS tip rib
2006-01-04 19:49 | 2006-01-04 20:35 | 0.031713 | 5.0698 | T10-03 VS rib
2006-01-04 00:20 | 2006-01-04 01:04 | 0.030394 | 5.0381 | T10-02 VS rib
2006-01-02 22:00 | 2006-01-02 23:06 | 0.045498 | 5.0077 | T08-01 vertical stabiliser frame
2006-01-02 15:29 | 2006-01-02 15:56 | 0.018935 | 4.9622 | T08-01 vertical stabiliser layout
2006-01-02 14:40 | 2006-01-02 15:15 | 0.024433 | 4.9433 | tidy up work area
2006-01-02 14:33 | 2006-01-02 14:40 | 0.0049537 | 4.9188 | T09-01 VS main spar assy (bolt holes)
2006-01-02 | 2006-01-02 01:15 | 0.052234 | 4.9139 | T09-01 VS main spar assy (bolt holes)
2005-12-21 22:42 | 2005-12-22 00:58 | 0.09478 | 4.8617 | T09-01 VS main spar assy
2005-12-21 21:47 | 2005-12-21 22:04 | 0.011771 | 4.7669 | T09-01 VS main spar assy
2005-12-21 20:57 | 2005-12-21 21:47 | 0.034456 | 4.7551 | T12-01 VS main spar aft strap (redrill laser holes)
2005-12-21 20:21 | 2005-12-21 20:56 | 0.024653 | 4.7206 | T12-03 VS upper spar channel
2005-12-21 19:37 | 2005-12-21 20:13 | 0.02515 | 4.696 | T09-02 VS fwd spar assy
2005-12-21 19:19 | 2005-12-21 19:37 | 0.012465 | 4.6708 | T12-10 clip
2005-12-21 00:18 | 2005-12-21 00:33 | 0.010417 | 4.6584 | T09-02 VS fwd spar assy
2005-12-20 23:18 | 2005-12-21 00:18 | 0.041979 | 4.648 | T12-08 VS forward spar channel
2005-12-20 22:56 | 2005-12-20 23:18 | 0.015289 | 4.606 | T09-03 temporary spacer (made from spare 2.5x2.5x1/8 angle)
2005-12-19 21:17 | 2005-12-19 22:21 | 0.044132 | 4.5907 | T08-01 vertical stabiliser familiarisation (confusion about what kit stock to make T09-03 (and other thick sheet parts) from)
2005-12-12 22:49 | 2005-12-12 23:04 | 0.010509 | 4.5466 | T08-01 vertical stabiliser review & parts inventory
2005-12-12 21:54 | 2005-12-12 22:49 | 0.037951 | 4.5361 | T02-03 elevator assy (redrill to #30)
2005-12-11 11:06 | 2005-12-11 12:43 | 0.067593 | 4.4981 | T02-02 HS assy (disassemble for final part cleanup & alodining)
2005-12-11 10:28 | 2005-12-11 11:05 | 0.025752 | 4.4305 | T02-03 elevator assy (fit to HS & install root assy)
2005-12-10 23:37 | 2005-12-11 00:35 | 0.039988 | 4.4048 | T02-03 elevator assy (fit to HS & install root assy)
2005-12-10 18:53 | 2005-12-10 19:39 | 0.032025 | 4.3648 | T02-02 assy (redrill skin holes to #30)
2005-12-10 16:37 | 2005-12-10 17:58 | 0.056157 | 4.3327 | T02-02 assy (redrill skin holes to #30)
2005-12-10 14:07 | 2005-12-10 15:11 | 0.044456 | 4.2766 | T07-01R&L elevator skins (retrim inboard end to correct angle)
2005-12-09 20:36 | 2005-12-09 21:28 | 0.035961 | 4.2321 | T06-02 elevator root assy (check dimensions - seems too big) - elevator horn is correct; my mistake was cutting the inboard end of the elevator skins with the lower surface laying flat instead of the upper surface. This has thrown the cut angle out around both the vertical and longitudonal axis. Luckily another result is that the skins have ended up too long, so I should be able to re-trim them correctly.
2005-12-08 20:53 | 2005-12-08 21:55 | 0.04272 | 4.1962 | T02-03 elevator assy (install T06-02 root assy)
2005-12-08 19:40 | 2005-12-08 20:42 | 0.043229 | 4.1534 | T02-03 RH elevator (drill hinge & ribs in place)
2005-12-07 21:34 | 2005-12-07 22:05 | 0.021481 | 4.1102 | T02-03 RH elevator (drill hinge & ribs in place)
2005-12-07 18:25 | 2005-12-07 20:37 | 0.091759 | 4.0887 | T02-03 LH elevator (drill hinge & ribs in place)
2005-12-06 21:57 | 2005-12-06 22:35 | 0.026204 | 3.997 | T07-08 elevator hinges (drill pilot holes)
2005-12-06 21:26 | 2005-12-06 21:58 | 0.022072 | 3.9708 | T02-03 elevator assy
2005-12-06 19:20 | 2005-12-06 20:30 | 0.048854 | 3.9487 | T07-01L&R elevator skins (trailing edge to fence; cut and pull
2005-12-06 19:13 | 2005-12-06 19:20 | 0.0046412 | 3.8998 | T06-02 elevator root assy (don't drill holes in 4130 steel with high-speed air-drill!)
2005-12-06 12:00 | 2005-12-06 12:30 | 0.020833 | 3.8952 | T06-02 elevator root assy (don't drill holes in 4130 steel with high-speed air-drill!)
2005-12-05 20:30 | 2005-12-05 21:00 | 0.020856 | 3.8744 | T06-02 elevator root assy
2005-12-05 16:43 | 2005-12-05 17:15 | 0.022176 | 3.8535 | T02-02 assy (T06-04 hinges)
2005-12-04 21:44 | 2005-12-04 22:02 | 0.012558 | 3.8313 | T02-02 assy (T06-04 hinges)
2005-12-04 20:41 | 2005-12-04 21:44 | 0.043657 | 3.8188 | T02-02 assy (T05-01L&R skin attach)
2005-12-04 15:47 | 2005-12-04 17:09 | 0.05706 | 3.7751 | T02-02 assy (T05-01L&R skin attach)
2005-12-04 13:30 | 2005-12-04 15:21 | 0.07728 | 3.7181 | T02-02 assy (T05-01L&R skin attach)
2005-12-04 12:54 | 2005-12-04 13:30 | 0.025336 | 3.6408 | T02-02 substructure assy (T04-06 LE ribs)
2005-12-04 11:08 | 2005-12-04 12:24 | 0.052431 | 3.6155 | T02-02 substructure assy (redrill to #30)
2005-12-02 22:38 | 2005-12-02 23:48 | 0.048507 | 3.563 | T02-02 substructure assy (drill ribs into position)
2005-12-02 19:08 | 2005-12-02 19:43 | 0.024514 | 3.5145 | T04-04L&R
2005-12-01 22:37 | 2005-12-01 23:08 | 0.021817 | 3.49 | T04-03L&R
2005-12-01 22:14 | 2005-12-01 22:37 | 0.015775 | 3.4682 | T04-02R
2005-12-01 20:02 | 2005-12-01 21:28 | 0.05978 | 3.4524 | T04-02L
2005-12-01 17:23 | 2005-12-01 18:14 | 0.035347 | 3.3926 | T02-02 HS substructure assy (T04-01 ribs)
2005-11-30 20:24 | 2005-11-30 22:02 | 0.068252 | 3.3573 | T02-02 HS substructure assy
2005-11-30 19:33 | 2005-11-30 20:24 | 0.035185 | 3.289 | T03-05 HS forward spar assy
2005-11-30 17:03 | 2005-11-30 18:06 | 0.043692 | 3.2538 | T03-05 HS forward spar assy
2005-11-29 21:54 | 2005-11-29 22:09 | 0.010359 | 3.2102 | T03-05 HS forward spar assy
2005-11-29 20:28 | 2005-11-29 21:54 | 0.059514 | 3.1998 | T03-06 HS forward spar channel (x2)
2005-11-29 20:23 | 2005-11-29 20:29 | 0.0039352 | 3.1403 | F15-05 (x2)
2005-11-29 19:55 | 2005-11-29 20:23 | 0.01912 | 3.1363 | T03-01 HS main spar assy
2005-11-29 02:58 | 2005-11-29 04:19 | 0.056134 | 3.1172 | T03-01 HS main spar assy
2005-11-29 01:42 | 2005-11-29 02:58 | 0.05294 | 3.0611 | T03-04 HS main spar channel (2)
2005-11-28 21:31 | 2005-11-28 22:10 | 0.027187 | 3.0081 | horizontal stabiliser parts layout
2005-11-28 19:18 | 2005-11-28 21:13 | 0.080174 | 2.981 | 0.060 sheet parts, W12-04(2), W11-04(2), G01-07RL, F15-05, W23-05
2005-11-27 21:12 | 2005-11-27 22:15 | 0.043437 | 2.9008 | 0.060 sheet parts T12-06, 09
2005-11-27 20:04 | 2005-11-27 20:33 | 0.020081 | 2.8573 | 0.060 sheet cut layout
2005-11-27 16:44 | 2005-11-27 17:28 | 0.030718 | 2.8373 | 0.060 sheet parts, T06-05 (2)
2005-11-27 13:47 | 2005-11-27 15:51 | 0.086354 | 2.8066 | 0.060 sheet parts, T06-05 (1 + 1 scrapped)
2005-11-27 11:36 | 2005-11-27 13:30 | 0.079155 | 2.7202 | horizontal stabiliser plans review
2005-11-26 13:47 | 2005-11-26 19:16 | 0.22868 | 2.641 | cut all channel material to length
2005-11-24 19:37 | 2005-11-24 21:38 | 0.083981 | 2.4124 | channel cut list check
2005-11-23 20:00 | 2005-11-23 23:00 | 0.12513 | 2.3284 | channel inventory & preliminary work
2005-07-18 21:29 | 2005-07-18 22:01 | 0.022512 | 2.2033 | W21-03/04/06/07 aileron pivot angles
2005-07-18 19:10 | 2005-07-18 20:35 | 0.059375 | 2.1807 | W21-03/04/06/07 aileron pivot angles
2005-07-17 14:53 | 2005-07-17 17:15 | 0.098356 | 2.1214 | T03-02 tailplane spar fitting
2005-07-17 12:46 | 2005-07-17 13:59 | 0.051019 | 2.023 | T03-02 tailplane spar fitting
2005-07-16 23:01 | 2005-07-16 23:15 | 0.0097338 | 1.972 | W21-03/04 right aileron bellcrank pivot angles
2005-07-16 22:24 | 2005-07-16 23:01 | 0.025579 | 1.9623 | W13-02L root rib attach angle
2005-07-16 17:24 | 2005-07-16 18:23 | 0.041042 | 1.9367 | W13-02R root rib attach angle
2005-07-16 12:40 | 2005-07-16 13:31 | 0.035741 | 1.8956 | T12-05 vertical stab attach angle
2005-07-16 00:09 | 2005-07-16 01:06 | 0.039618 | 1.8599 | T03-03 horiz stab attach angles (2)
2005-07-15 21:11 | 2005-07-15 22:01 | 0.03478 | 1.8203 | F23-03/04 tailwheel mounts
2005-07-12 19:44 | 2005-07-12 20:45 | 0.0425 | 1.7855 | F23-03/04 tailwheel mounts
2005-07-12 18:40 | 2005-07-12 19:44 | 0.044109 | 1.743 | F22-05 aft angle
2005-07-11 22:36 | 2005-07-11 23:55 | 0.05515 | 1.6989 | F16-06R&L vertical angles
2005-07-09 22:37 | 2005-07-09 23:24 | 0.03235 | 1.6437 | F10-05R&L seat belt attach brackets
2005-07-09 21:11 | 2005-07-09 22:29 | 0.054387 | 1.6114 | F16-04 support angle
2005-07-09 19:17 | 2005-07-09 19:30 | 0.0092477 | 1.557 | F16-04 support angle
2005-07-09 18:15 | 2005-07-09 18:47 | 0.02206 | 1.5478 | F16-09 cross tie
2005-07-09 15:41 | 2005-07-09 17:12 | 0.063391 | 1.5257 | F15-07R&L, F15-12R&L flap drive mounts
2005-07-08 22:57 | 2005-07-09 00:07 | 0.048669 | 1.4623 | F15-04R&L rudder pedal mount angles
2005-07-07 21:15 | 2005-07-07 23:46 | 0.10458 | 1.4136 | F15-02R&L engine mount attach brackets
2005-07-06 00:12 | 2005-07-06 02:18 | 0.087164 | 1.3091 | F15-01R&L engine mount attach brackets
2005-07-05 20:23 | 2005-07-05 22:31 | 0.088738 | 1.2219 | F15-01R&L engine mount attach brackets
2005-07-03 20:28 | 2005-07-03 22:33 | 0.086667 | 1.1331 | F14-12R&L (seat belt attach)
2005-07-02 20:42 | 2005-07-02 22:38 | 0.080312 | 1.0465 | D02-14, F10-19, F10-20, F14-13R&L
2005-07-02 17:20 | 2005-07-02 19:28 | 0.088912 | 0.96617 | F14-02R&L, L05-07, D02-14
2005-07-02 13:23 | 2005-07-02 14:23 | 0.041667 | 0.87726 | F14-07R&L
2005-06-30 19:39 | 2005-06-30 22:24 | 0.11432 | 0.83559 | F14-08R&L (took a while!)
2005-06-29 21:44 | 2005-06-29 23:56 | 0.091354 | 0.72127 | F03-05L&R, F03-06L&R
2005-06-28 22:56 | 2005-06-28 23:57 | 0.042106 | 0.62992 | W11-07, tablesaw test
2005-06-27 22:19 | 2005-06-27 23:34 | 0.052303 | 0.58781 | W11-05x1, W11-08x2
2005-06-27 18:42 | 2005-06-27 20:38 | 0.080509 | 0.53551 | W11-10LR, W11-09x2, W11-11x2
2005-06-26 21:03 | 2005-06-27 00:42 | 0.15185 | 0.455 | F10-06, F14-11LR, F22-06
2005-06-23 22:53 | 2005-06-24 00:07 | 0.05125 | 0.30315 | cut 1' angle
2005-06-21 21:36 | 2005-06-21 23:33 | 0.081169 | 0.2519 | cut angle
2005-06-21 19:26 | 2005-06-21 21:25 | 0.082616 | 0.17073 | cut angle
2005-06-20 22:01 | 2005-06-21 00:08 | 0.088113 | 0.088113 | cut aluminium angle kit to lengths
Formulas:
End Time = [Start Time]+[Duration]